## Definitions
Definitions for Quarterly Status Spreadsheet Terms
Term | Definition
CAP | Corrective Action Plan. A series of steps/actions an agency plans to take to correct the issue(s) identified in a finding.
CAP Status | "Complete" means all steps of an agency's CAP are complete and the issue identified in the finding should not recur. "In Process" means not all CAP steps have been completed as yet. "N/A" signifies the agency's disagreement with a finding and that they feel no CAP is necessary.
Finding # | The finding number as designated in the Single Audit report. The first four digits indicate the year, e.g. 2023-XXX.
Questioned Costs | As defined in the Uniform Grant Guidance (UGG), 2 CFR Part 200.84, questioned cost means a cost that is questioned by the auditor because of an audit finding: (a) Which resulted from a violation or possible violation of a statute, regulation, or the terms and conditions of a Federal award, including for funds used to match Federal funds; (b) Where the costs, at the time of the audit, are not supported by adequate documentation; or (c) Where the costs incurred appear unreasonable and do not reflect the actions a prudent person would take in the circumstances.
Resolution Status | "Resolved" means the agency has received a resolution letter (i.e. correspondence indicating that the CAP is considered to be adequate) from the federal agency responsible for resolving the finding. "Unresolved" means the agency has not yet received a resolution letter from the federal agency. "Closed" signifies that a finding has been closed in accordance with UGG, 2 CFR Part 200.511 which states:
(3) ...A valid reason for considering an audit finding as not warranting further action is that all of the following have occurred:
(i) Two years have passed since the audit report in which the finding occurred was submitted to the Federal Audit Clearinghouse (FAC);
(ii) The Federal agency or pass-through entity is not currently following up with the auditee on the audit finding; and
(iii) A management decision was not issued.

## Federal Agency Abbreviations
Federal Agency Abbreviations
Abbreviation | Federal Agency
DHS | United States Department of Homeland Security
DOD | United States Department of Defense
DOE | United States Department of Energy
DOI | United States Department of the Interior
DOJ | United States Department of Justice
DOL | United States Department of Labor
DOT | United States Department of Transportation
DVA | United States Department of Veterans Affairs
EPA | United States Environmental Protection Agency
HHS | United States Department of Health and Human Services
HUD | United States Department of Housing and Urban Development
TREAS | United States Treasury
USDA | United States Department of Agriculture
USDE | United States Department of Education

## DDAP
Status of Unresolved Audit Findings - Department of Drug and Alcohol Programs
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 06-30-2024
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2023-007 | A Significant Deficiency and Noncompliance Exist at the Department of Drug and Alcohol Programs Related to Submission of Performance Progress Reports | HHS-SAMHSA | N/A | N/A | Complete | Unresolved | CAP implemented. Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | In Process | Unresolved | The Department’s Division of County Oversight Programs (CPO) has revised the process used to monitor the SCAs to incorporate a review of SOR data submitted by the SCAs and reported by the Department of the Performance Progress Report (PPR). A policy was developed, review instruments were revised, and Project Officers were informed and trained on the changes to the monitoring process and ensuring the accuracy of the SOR data. The Substance Abuse and Mental Health Services Administration (SAMHSA) sent DDAP correspondence in June 2024 requesting information in order to resolve the audit finding. DDAP provided a response to SAMHSA on July 24, 2024 and is currently waiting on a response.

## DHS
Status of Unresolved Audit Findings - Department of Human Services
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 6-30-2024 |  |  | Resolution as of 3-31-2024 |  |  | Resolution as of 12-31-2023 |  |  | Resolution as of 09-30-2023 |  |  | Resolution as of 06-30-2023
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2022-006 | A Material Weakness and Material Noncompliance Exist at the Department of Human Services Related to Electronic Benefits Transfer Card Security | HHS-ACF, USDA | 2021-005 | N/A | Complete | Closed | This finding has been closed in accordance with UGG, 2 CFR Part 200.511. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution from USDA. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution from USDA. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution from USDA. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution from USDA. | Complete | Unresolved | The CAP is complete for this finding. Awaiting USDA resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting USDA resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution.
2022-009 | A Significant Deficiency and Noncompliance Exist at the Department of Human Services Related to the Medicaid National Correct Coding Initiative | HHS-CMS | 2021-009 | N/A | Complete | Closed | This finding has been closed in accordance with UGG, 2 CFR Part 200.511. | Complete | Unresolved | See Finding 2023-016. | Complete | Unresolved | See Finding 2023-016. | Complete | Unresolved | See Finding 2023-016. | Complete | Unresolved | Final amendment will be added to the contract by June 30, 2024. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | OMAP’s Bureau of Data and Claims Management (BDCM) executed the amendment to the PROMISe contract with Gainwell Technologies which includes the necessary NCCI Confidentiality Agreement.
2023-012 | A Material Weakness and Material Noncompliance Exist at the Department of Human Services Related to Electronic Benefits Transfer Card Security | HHS-ACF, USDA | 2022-006 | N/A | Complete | Unresolved | The CAP is complete. Received HHS resolution letter, need USDA resolution letter. | In Process | Unresolved | The Bureau of Program Evaluation, Division of Corrective Action began their next review cycle in October 2024; the rest of the CAP is complete. Received HHS resolution letter, need USDA resolution letter. | In Process | Unresolved | The Bureau of Program Evaluation, Division of Corrective Action began their next review cycle in October. | In Process | Unresolved | The Bureau of Program Evaluation, Division of Corrective Action will begin their next review cycle in October 2024; the rest of the CAP is complete.
2023-015 | A Material Weakness and Material Noncompliance Exist in the Department of Human Services’ Program Monitoring of the Social Services Block Grant Subrecipients | HHS-ACF | N/A | N/A | In Process | Unresolved | Monitoring is ongoing for OPD and OA during FY 24/25. | In Process | Unresolved | Monitoring is ongoing for OA. For OPD, the risk assessments have been completed and monitoring is ongoing. | In Process | Unresolved | OPD is continuing to conduct monitoring procedures. | In Process | Unresolved | The CAP is complete for OA. For OPD, the risk assessments have been completed and monitoring is ongoing.
2023-016 | A Significant Deficiency and Noncompliance Exist at the Department of Human Services Related to the Medicaid National Correct Coding Initiative | HHS-CMS | 2022-009 | N/A | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | Final amendment was added to the contract in June 2024.
2023-023 | State Agencies Did Not Identify the Federal Award Information and Applicable Requirements at the Time of the Subaward and Did Not Evaluate Each Subrecipient’s Risk of Noncompliance as Required by the Uniform Grant Guidance | HHS-ACF,ARD | 2022-013 | N/A | In Process | Resolved | OPD risk assessments have been completed and monitoring is ongoing. The risk assessment for Foster Care is being completed during FY 24-25. | In Process | Resolved | For the Federally-required award information, OCYF included this information for Foster Care in the FY 24-25 allocation letters. The risk assessment for Foster Care will be completed during FY 24-25. For OPD (TANF and SSBG), the monitoring is ongoing. Received HHS-ACF resolution letter for TANF. | In Process | Unresolved | The FC risk assessment is being conducted during FY 24-25. For OPD (TANF and SSBG), monitoring is ongoing. Federal resolution was received from HHS-ACF for SSBG and FC, still need for TANF. Federal resolution was received from HHS-ARD. | In Process | Unresolved | For the Federally-required award information, OCYF will include this information for Foster Care in the FY 24-25 allocation letters. The risk assessment for Foster Care will be completed during FY 24-25. For OPD (TANF and SSBG), the risk assessments have been completed and monitoring is ongoing.

## DOC
Status of Unresolved Audit Findings - Department of Corrections
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 06-30-2024
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2023-006 | A Material Weakness and Material Noncompliance Exist at the Department of Corrections Related to the Review of Opioid Medication Costs | HHS-SAMHSA | N/A | N/A | Complete | Unresolved | CAP implemented. Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | Starting with January through March 2024, the DOC has begun a process to review drug costs on a quarterly basis. The DOC requests from the medication vendor, Diamond, their supplier invoices to verify the cost is being invoiced to the DOC at cost plus a dispensing fee. The DOC tests the opioid medication as well as a random selection of other medications provided. The results of the January through March 2024 testing were that the medications were being billed per the contract at cost plus the distribution fee.

## DOH
Status of Unresolved Audit Findings - Department of Health
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 6-30-2024 |  |  | Resolution as of 3-31-2024 |  |  | Resolution as of 12-31-2023 |  |  | Resolution as of 09-30-2023 |  |  | Resolution as of 06-30-2023
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Description | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2022-013 | State Agencies Did Not Identify the Federal Award Information and Applicable Requirements at the Time of the Subaward and Did Not Evaluate Each Subrecipient’s Risk of Noncompliance as Required by the Uniform Grant Guidance | HHS-CDC | N/A | N/A | Complete | Closed | This finding has been closed in accordance with UGG, 2 CFR Part 200.511. | In Process | Unresolved | See Finding 2023-023. | In Process | Unresolved | See Finding 2023-023. | In Process | Unresolved | See Finding 2023-023. | In Process | Unresolved | Monitoring division given a new target date to be fully operational March 31, 2025. | In Process | Unresolved | Contractors are in negotiation for the monitoring division. | In Process | Unresolved | No change in Education Portion. Assessment portion completion is delayed due to lack of state funding for the Monitoring division. Contractors and alternatives are being considered for the Monitoring division. | In Process | Unresolved | The following CAP portion is currently awaiting legal and leadership review and approval: Educate Department: Budget Office is developing a bulletin that will outline the subrecipient monitoring requirements with links to State and Federal Sources. The bulletin will be shared with all program office staff. The Budget Office will develop the following templates and provide to all program offices: - Determination of vendor status: Subrecipient or Contractor - Risk Assessment Form - Internal Control Self-Assessment for Subrecipient Template - Subrecipient Monitoring Template
2022-014 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | USDA | N/A | N/A | Complete | Closed | This finding has been closed in accordance with UGG, 2 CFR Part 200.511. | Complete | Unresolved | CAP is complete. Awaiting federal resolution. | Complete | Unresolved | CAP is complete. Awaiting federal resolution. | Complete | Unresolved | Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution. | Complete | Unresolved | The CAP is complete for this finding. Awaiting federal resolution.
2023-023 | State Agencies Did Not Identify the Federal Award Information and Applicable Requirements at the Time of the Subaward and Did Not Evaluate Each Subrecipient’s Risk of Noncompliance as Required by the Uniform Grant Guidance | HHS-CDC | 2022-013 | N/A | In Process | Unresolved | The consulting firm shared recommendations based on their gap analysis and are working to create proposed draft policies and procedures to address the risks identified. Policies and procedures updates are to be implemented by May 20, 2025. | In Process | Unresolved | DOH engaged the services of a consulting firm to survey and assess current practices, documentation and training materials across the agency including the materials and pilot mentioned last quarter: They will: - Identify gaps in knowledge and processes across the agency. - Consultant to provide findings to PA DOH. - Provide recommended edits and additions for future policies, procedures, and template updates. - Provide training materials. - Conduct extensive training across the department. | In Process | Unresolved | Drafted comprehensive guidance with templates and sent to 3 program offices to pilot the guidelines. New proposal was submitted to restructure the budget office and leverage existing positions and federal funding for subrecipient monitoring division. The proposal is with the Budget Secretary. | In Process | Unresolved | Monitoring Division job descriptions have been drafted and are now being reviewed.
2023-024 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | HHS-ARD,CDC, USDA | 2022-014 | N/A | Complete | Unresolved | CAP is complete. Awaiting HHS-CDC resolution. | Complete | Unresolved | CAP is complete. Awaiting HHS-CDC resolution. | Complete | Unresolved | USDA and HHS-ARD sent resolution correspondence. Awaiting HHS-CDC resolution. | Complete | Unresolved | CAP is complete. Awaiting federal resolution.

## L&I
Status of Unresolved Audit Findings - Department of Labor and Industry
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 06-30-2024
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2023-017 | Inappropriate Privileged Access Granted to Program Personnel | USDE | N/A | N/A | Complete | Unresolved | CAP implemented. Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | OA completed CAP implementation and is awaiting resolution from USDE.
2023-018 | A Significant Deficiency and Noncompliance Exist in the Department of Labor and Industry’s Procedures Related to Period of Performance Requirements | USDE | N/A | 8763 | Complete | Unresolved | CAP implemented. Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | The error was corrected and the grant end reconciliation procedures are in place to avoid the issue in the future.
2023-019 | A Significant Deficiency and Noncompliance Exist Related to the Preparation and Submission of the Quarterly RSA-17 Report | USDE | N/A | N/A | Complete | Unresolved | CAP implemented. Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | L&I OVR implemented a policy that has Budget and Admin Division Chief and the CFO to review the submitted RSA-17 reports for errors. A revised RSA-17 was submitted on March 12, 2024.

## OA
Status of Unresolved Audit Findings - Office of Administration
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 6-30-2024
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2023-017 | Inappropriate Privileged Access Granted to Program Personnel | USDE | N/A | N/A | Complete | Unresolved | CAP implemented. Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | OA completed CAP implementation and is awaiting resolution from USDE.

## OB
Status of Unresolved Audit Findings - Office of the Budget
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 6-30-2024
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2023-019 | Significant Deficiency and Noncompliance Related to the Preparation and Submission of the Quarterly RSA-17 Report | USDE | N/A | N/A | Complete | Unresolved | CAP implemented. Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | OB-BAFM revised procedures to include having both the reviewer and preparer match the PDF output to the final Excel spreadsheet. The finding and procedure change was discussed with the applicable staff. L&I OVR implemented a policy that has Budget and Admin Division Chief and the CFO to review the submitted RSA-17 reports for errors. A revised RSA-17 was submitted on March 12, 2024.

## PDA
Status of Unresolved Audit Findings - Department of Agriculture
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 06-30-2024
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2023-023 | State Agencies Did Not Identify the Federal Award Information and Applicable Requirements at the Time of the Subaward and Did Not Evaluate Each Subrecipient’s Risk of Noncompliance as Required by the Uniform Grant Guidance | USDA | N/A | N/A | In Process | Unresolved | PDA is still in the process of implementing the plan for subrecipient risk assessment. We now anticipate a completion date of this corrective action by 6/30/25. | In Process | Unresolved | For TEFAP sub-award recipients (Food Banks), updated contracts were implemented in November and December 2024. These updated contracts included the relevant FAINs and ALNs on the contract headings, and Single Audit instructions as part of the agreements. PDA is in the process of implementing our plan to evaluate in advance, subrecipients' risk of noncompliance with Federal statutes, regulations, and the terms and conditions of the sub-award and to provide timely performance check-ins and follow-ups as needed. Originally, PDA had planned to finalize implementation of this CAP by 6/30/2024. With three vacancies in our budget/fiscal office having existed since July 2024, full implementation has depended on getting those positions back-filled. As these positions were finally filled in January 2024, we now anticipate a completion date of this corrective action by 5/31/25. | In Process | Unresolved | PDA has executed sub-award agreements with TEFAP recipient agencies. Going forward, PDA will annually evaluate sub-awardees in advance of providing funds based on the following criteria: (1) The subrecipient’s prior experience with the same or similar subawards; (2) The results of previous audits including whether or not the subrecipient receives a Single Audit, and the extent to which the same or similar subaward has been audited as a major program; (3) Whether the subrecipient has new personnel or new or substantially changed systems; and (4) The extent and results of a Federal awarding agency's own monitoring of other Federal awards directly to the sub-recipient of this program. PDA is still in the process of implementing our plan to evaluate in advance subrecipients' risk of noncompliance with Federal statutes, regulations, and the terms and conditions of the sub-award and to provide timely performance check-ins and follow-ups as needed. Originally, PDA had planned to finalize implementation of this CAP by 6/30/2024. With three vacancies in our budget/fiscal office, full implementation depends on getting those positions back-filled, with at least one dedicated to Federal grant activity. We anticipate the first vacancy, a Fiscal Management Specialist 2, to be filled in early November. | In Process | Unresolved | Letters to existing TEFAP sub-award recipients were issued, providing them with the relevant FAINs and ALNs for their respective contracts and to remind them of their contractual obligations with regards to Single Audit filing requirements. PDA is currently working to execute sub-award agreements with TEFAP recipient agencies for the TEFAP Reach and Resiliency Round 2 sub-grants and will include FAINs, ALNs, and Single Audit instructions as part of these agreements. PDA is still in the process of developing and implementing a process to address the following: PDA’s process for evaluating subrecipient’s risk of noncompliance with Federal statutes, regulations, and the terms and conditions of the sub-award, specifically: • risk assessment for determining compliance. • specific questions related to an organization’s ability to follow all terms and conditions of the agreement. • performance check-ins. • follow ups as needed. Originally, PDA had planned to finalize implementation of this CAP by 6/30/2024. As this is still in-process, we are now proposing to complete this CAP by 9/30/2024.
2023-024 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | USDA | N/A | N/A | In Process | Unresolved | The mgmt specialist 2 has now been onboarded and has begun processing Single Audit resolutions for the Bureau of Food Assistance. Over the next quarter, the Bureau of Foos Assistance will work with this individual and with the Bureau of Administrative Services to document the policies and procedures that have been put in place for the subrecipient audit resolution process. The anticipated completion date of developing and documenting policies and procedures is 6/30/25. | In Process | Unresolved | The individual filling the Fiscal Management Specialist 2 position began work with the PDA Bureau of Administrative Services, Office of the Budget in mid-January 2025. This individual is currently being onboarded into her position and has begun to meet with staff in the Bureau of Food Assistance to understand the work of the Bureau and the scope of the single audits. Having this individual on board now provides the capacity to both develop and document policies and procedures for the subrecipient audit resolution process. Because the hiring process took longer than expected, the new anticipated completion date of developing and documenting policies and procedures is 5/31/25.. | In Process | Unresolved | A Fiscal Management Specialist 2 position closed on 10/13/24 and candidates were selected for interviews on 10/17/24. Pending a background check on the selectee, the position should be filled in early November, creating capacity to both develop and document policies and procedures for the subrecipient audit resolution process. The Financial Management Specialist 2 will work to resolve both the outstanding audit resolutions and the identified weaknesses that cause untimely subrecipient Single Audit resolution, including untimely management decisions on findings, untimely review of the SEFA or alternate procedures, and late audit report submissions be corrected to ensure compliance with federal requirements and Commonwealth Management Directives, and to better ensure timelier subrecipient compliance with program requirements. Anticipated completion date of developing and documenting policies and procedures is 3/31/2025. | In Process | Unresolved | Recognizing that our agency does not have documented policies and processes established for subrecipient audits, a new complement position was created. A Fiscal Management Specialist 1 was added to our complement in June 2024. A requisition was submitted to HR and the position is in the process of being posted. Anticipated completion date is 9/30/2024.

## PDOA
Status of Unresolved Audit Findings - Department of Aging
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 06-30-2024
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2023-002 | A Material Weakness and Material Noncompliance Exist in the Department of Aging’s Maintenance of Effort Certification Reporting Process | HHS-ACL | N/A | N/A | Complete | Unresolved | CAP implemented. Awaiting federal resolution. Finding was not repeated. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | The PA Department of Aging realized that the MOE for FY 2022 was submitted as confirmed by HHS-ACL. The completed form was provided to the Single Audit Resource Account on May 7, 2024. PDOA has since reached out to HHS-ACL several times requesting a decision letter to consider this matter resolved.
2023-003 | A Material Weakness and Material Noncompliance Exist in the Department of Aging Related to Subrecipient Monitoring | HHS-ACL | N/A | N/A | Complete | Unresolved | CAP implemented. Awaiting federal resolution. | Complete | Unresolved | PDOA has confirmed receipt of completed Risk Assessments for the entire AAA network in Pennsylvania. Evaluations have been completed as of January 14, 2025 and performance Improvement Plans have been distributed to those found not in compliance in preparation of the Phase IX monitoring. PDOA considers these actionable steps taken toward resolve of this CAP to consider its status as complete but pending confirmation from ACL. | In Process | Unresolved | The FMS2 that started in June discontinued employment with the Commonwealth. Interviews to fill the vacancy restarted and a new FMS2 has started effective October 28, 2024. PDOA has since finalized the Risk Assessment Tool, distributed across the entire AAA Network, and evaluations are currently underway for 33 of the 52 AAAs. PDOA now anticipates a completion date of December 1, 2024. | In Process | Unresolved | A new element in the Comprehensive Aging Performance Evaluation Monitoring launched in April of 2024 to monitor timely reporting submissions. The Fiscal Management Specialist II started June 10, 2024 with a updated position description to reflect the following actions be taken through a Risk Assessment Tool: Perform risk based during-the-award monitoring procedures for all Aging Cluster subrecipients to ensure timely compliance with all applicable federal regulations. Responsibilities include but are not limited to coordinating emails, conducting on-site or virtual risk assessments, and reporting the conclusions reached as a result. Submit written documentation and samples of unresolved patterns of noncompliance to supervisor for submission to the Finance Director. Evaluate each subrecipient’s risk of noncompliance to proactively address any weaknesses in internal controls over federal programs. Assess program performance and implement corrective action to ensure optimum results. PDOA now anticipates a completion date of October 1st, 2024.
2023-023 | State Agencies Did Not Identify the Federal Award Information and Applicable Requirements at the Time of the Subaward and Did Not Evaluate Each Subrecipient’s Risk of Noncompliance as Required by the Uniform Grant Guidance | HHS-ACL | N/A | N/A | Complete | Unresolved | The Phase IX Fiscal Review launched at the end of April which includes an entire section specific to subrecipient monitoring to verify that AAAs have a documented plan for handling subrecipient issues. This step was made in addition to the adjustments made to the Aging Program Directives published on the Department of Aging's website regarding Federal Award Identification as shown in the most recent publication of APD 25-01-03. Improvements continue to be made and PDOA now considers this CAP complete. | In Process | Unresolved | In addition to the adjustments made to the Aging Program Directives published on the Department of Aging's website regarding Federal Award Identification, PDOA confirmed the Comprehensive Aging Performance Evaluation a success and shifted it out of pilot status. This finding has aided in our approach to the subrecipient section of contract language as the Cooperative Block Grants are actively being developed at this time. The proposed policy has been addressed Subrecipient requirements in the Admin Chapter as opposed to the appendix. Improvements continue to be made and PDOA now anticipates a completion date of March 1, 2025. | In Process | Unresolved | Adjustments have been made to the Aging Program Directives published to the network to properly identify the Federal Award Identification cited in the finding. The FMS2 that started in June discontinued employment with the Commonwealth. Interviews to fill the vacancy restarted and a new FMS2 has started effective October 28, 2024. PDOA has since finalized the Risk Assessment Tool, distributed across the entire AAA Network, and evaluations are currently underway for 33 of the 52 AAAs. Therefore we have met our expectation of reaching half at the minimum as identified in previous quarterly update. PDOA now anticipates a completion date of December 1, 2024. | In Process | Unresolved | With the use of a monitoring log, the PDOA plans to perform risk assessments systemically statewide for all Aging Cluster subrecipients. PDOA acknowledges although unavoidable due to timing last year, but can implement plans to roll out effective for FY starting July 1, 2024. Accordingly, a risk assessment is being developed to evaluate each subrecipient’s risk of noncompliance to proactively address any weaknesses in internal controls over Federal programs. The new element in the CAPE pilot to monitor timely reporting submissions has proven successful for three piloted Area Agencies on Aging. Performance Check-Ins launched in April of 2024 as part of a Statewide Comprehensive Monitoring as a new form of regulatory measure. The Fiscal Management Specialist II started June 10, 2024 with a position description updated to with Risk Assessment tasks. As a starting point, PDOA plans to prioritize the larger organizations which typically require more monitoring on an annual basis. Count Time Study Participants projected AAA 6 Allegheny, 11 Blair, 12 Bed/Fult.Hunt, 31 Philadelphia, and 37 Luzerne / Wyoming as top 5 in terms of employees. Subrecipient monitoring is projected to occur during the fiscal year ended June 30, 2023 for the Aging Cluster subrecipients to ensure timely compliance with all applicable federal regulations. This was confirmed as a current practice also within Phase VIII of fiscal monitoring and being taken into consideration of the draft of the Phase IX monitoring tool. PDOA recognizes time and insufficient staffing as a barrier to achieving the goal of performing a risk assessment for every AAA, but has set an expectation of reaching half at a minimum. -Two vacant FMS2 will be working in the Finance Department -The Fiscal Management Specialist I selected started work effective 7/29/2024 PDOA now anticipates a completion date of October 1st, 2024.
2023-024 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | HHS-ACL | N/A | N/A | In Process | Unresolved | The FMS2 position has been filled effective April 23, 2025. The New FMS2 has been provided with process mapping for the many processes developed including the subrecipient audit resolution process. Again, recognizing the amount of training required to develop an understanding of the process, PDOA now anticipates a completion date of June 30, 2025. | In Process | Unresolved | Unfortunately staffing retention continues to prove challenging as another FMS2 has decided to depart from the Bureau of Finance. Despite another set back, the position has been listed and interviews will be arranged in the near future to fill the vacancy. The New FMS2 will be provided with process mapping for the many processes developed including the subrecipient audit resolution process. Again, recognizing the amount of training required to develop an understanding and rhythm to the process, PDOA now anticipates a completion date of March 1, 2025. | In Process | Unresolved | New FMS2 hired effective October 28, 2024 to develop and maintain a desk review monitoring program for AAA network financial audits to ensure the accuracy of the reported information and correction of audit findings. Taking into consideration the amount of training required to complete this task, PDOA now anticipates a completion date of January 1, 2025. | In Process | Unresolved | As detailed in the Corrective Action Plan, an audit tracking log has been established in the Agency Share folder. A separate tracking mechanism is in place to ensure the monitoring of subrecipient activities for compliance via the Regional tracker of the Phase VIII Audits. A statement of work has been developed and submitted for internal approval since the Central Region Representative has been reassigned to assist with the new CAPE monitoring efforts statewide. A Fiscal Management Specialist was hired effective May 18, 2024, to develop and maintain a desk review monitoring program for AAA network financial audits to ensure the accuracy of the reported information and correction of audit findings. PDOA now anticipates a completion date of October 1st, 2024.

## PDE
Status of Unresolved Audit Findings - Education
[5 empty] | Resolution as of 3-31-2025 |  |  | Resolution as of 12-31-2024 |  |  | Resolution as of 09-30-2024 |  |  | Resolution as of 6-30-2024 |  |  | Resolution as of 3-31-2024 |  |  | Resolution as of 12-31-2023 |  |  | Resolution as of 09-30-2023 |  |  | Resolution as of 06-30-2023
[5 empty] | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status |  |  | Status
Finding # | Finding Title | Resolution Federal Agency | Prior Year Finding | Questioned Costs | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding |  | CAP | Finding
2022-014 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | USDE, USDA | N/A | N/A | Complete | Closed | This finding has been closed in accordance with UGG, 2 CFR Part 200.511. | Complete | Unresolved | PDE is awaiting resolution from USDA and USDE. | Complete | Unresolved | PDE is awaiting resolution from USDA and USDE. | Complete | Unresolved | PDE is awaiting resolution from USDA and USDE. | Complete | Unresolved | CAP is complete. PDE is awaiting federal resolution. | Complete | Unresolved | CAP is complete. PDE is awaiting federal resolution. | Complete | Unresolved | CAP is complete. PDE is awaiting federal resolution. | In Process | Unresolved | PDE is finalizing the implementation of corrective action and is awaiting USDE's Program Determination Letter.
2023-024 | A Material Weakness and Material Noncompliance Exist in the Commonwealth’s Subrecipient Audit Resolution Process | USDE, USDA | 2022-014 | N/A | Complete | Unresolved | PDE is awaiting resolution from USDA and USDE. | Complete | Unresolved | PDE is awaiting resolution from USDA and USDE. | Complete | Unresolved | PDE is awaiting resolution from USDE and USDA. | Complete | Unresolved | PDE completed CAP implementation and is awaiting resolution from USDE and USDA.