## Slide 1: Professional Evaluations

## Slide 2: Why?
The purpose is to evaluate Professionals regarding their performance throughout the Project and to use their evaluation as criteria for selections of Professionals on future projects.
Tool to help ensure that we are selecting quality Professionals.
A means to reward Professionals that excel.
A tool to communicate with the Professional on whether they are meeting our expectations.

## Slide 3: What?
The following key performance indicators will be evaluated:
    Timeliness
    Quality
    Negotiations
    Invoices
    Budget
    Communication
    Sufficient Alternatives
    Project Procedures Manual (Rules)
    Estimating
    Magnitude of addenda
    Bid extensions
    Coordination
    Representation
    Site visits & reports
    Submittals
    Responsiveness
    e-Builder proficiency

## Slide 4: When?
Within 2 weeks of the following Project milestones:
  Completion of Negotiations
  DGS’s approval of 50% Design
  DGS’s approval of 100% Design
  Bid Opening – Upon commencement of the Fiscal Analysis (FA) Process
  The elapse of 50% of the original Construction duration
  The last Final Inspection on the Project
  BOC will evaluate at the elapse of 25% and 75% of the original Construction duration. However, the evaluations at these intervals will not contribute to the Professional Evaluation score.

## Slide 5: How?
The Bureau of Capital Projects Design’s evaluations will utilize a grade of 1, 3, or 5 to measure the Professional’s performance in relation to specific criteria. The Design Project Manager (DPM) will perform the evaluations during pre-construction. The Professional will receive a score for each criterion as follows:
  1 – Unsatisfactory
  3 – Satisfactory
  5 – Excellent

## Slide 6: How?
The Bureau of Construction’s evaluations will utilize a grade of 1, 3, or 5 to measure the Professional’s performance in relation to specific criteria. The Assistant Project Coordinator (APC) will perform the evaluations during construction. The Professional will receive a score for each criterion as follows:
  1 – Unsatisfactory
  3 – Satisfactory
  5 – Excellent

## Slide 7: Where? Forms
General Scoring Guidance
Specific Scoring Guidance
Required Comment Field

## Slide 8: Where? Forms
Example Question #1

## Slide 9: Where? Forms
Example Question #2

## Slide 10: Where? Forms
Example Question #3

## Slide 11: Professional Evaluations
Chart: Past Professional Selections Points
| BDISBO 200 Points | 800 Points
Current Professional Selections Points | 200 | 800

## Slide 12: Professional Evaluations
Chart: 
| Professional Evaluations 200 Points | 800 Points
Future Professional Selections Points | 200 | 800

## Slide 13: Professional Evaluations
Chart: 
| Negotiations | Design | Bidding & Award | Construction
Project Stage Contributions | 10 | 40 | 12 | 38

## Slide 14: Professional Evaluations
Phase | Possible Score
Negotiations | 15
50% Design | 31
100% Design | 31
Bidding & Award | 18
Pre-Construction Subtotal | 95
50% Construction | 29
100% Construction | 29
Construction Subtotal | 58
Pre-Construction & Construction Total | 153
Evaluation Percentage | Points Awarded
0-27% | 0
28-31% | 10
32-35% | 20
36-39% | 30
40-43% | 40
44-47% | 50
48-51% | 60
52-55% | 70
56-59% | 80
60-63% | 90
64-72% | 100
73-78% | 120
79-84% | 140
85-90% | 160
91-96% | 180
97-100% | 200
A Professional receiving satisfactory ratings for all criterion will be awarded 100 Points.
A Professional who has never worked on a DGS Project will be awarded 100 Points.
Satisfactory rating

## Slide 15: Professional Evaluations
Phase | Professional’s Score Project X | Professional’s Score Project Y | Possible Score
Negotiations | 11 | 13 | 30
50% Design | 25 | 27 | 62
100% Design | 27 |  | 31
Bidding & Award | 16 |  | 18
50% Construction | 25 |  | 29
100% Construction |  |  | 
Pre-Construction & Construction Total | 104 | 40 | 170
Evaluation Percentage | Points Awarded
0-27% | 0
28-31% | 10
32-35% | 20
36-39% | 30
40-43% | 40
44-47% | 50
48-51% | 60
52-55% | 70
56-59% | 80
60-63% | 90
64-72% | 100
73-78% | 120
79-84% | 140
85-90% | 160
91-96% | 180
97-100% | 200
The Professional in the example above has just completed 50% Construction on Project X and 50% Design on Project Y. The Professional’s Scores for each project are added together 104 + 40 = 144 and divided by the Possible Score of 170 and multiplied by 100 to get the Evaluation Percentage. 144/170 = 0.847 X 100 = 84.7 or 85% The Evaluation Percentage of 85% equates to 160 Points
Rating
Scoring Example

## Slide 16: Professional Evaluation Reports
Professional XYZ
50% Design
100% Design
Negotiations
Bidding & Awards
50% Construction
100% Construction
Negotiations
50% Design
100% Design
Bidding & Awards
50% Construction
100% Construction
Negotiations
100% Design
50% Construction
50% Design
Bidding & Awards
2020
2021
2022
2023
2024
3 Year Period
Project #1
Project #2
Project #3

## Slide 17: When?
Implementation Plan
Start collecting data in forms – July 2020
Start reporting – August 2020
Selections Applications due – August 5th, 2020
Governors Committee Meeting – September 10th, 2020
After this Webinar, the Forms will be posted to:
https://www.dgs.pa.gov/Design-and-Construction/Design

## Slide 18: Questions ?