COMMONWEALTH OF PENNSYLVANIA

DEPARTMENT OF HUMAN SERVICES

INFORMATION TECHNOLOGY GUIDELINE

| Name Of Guideline: | Number: |
| --- | --- |
| Implementation Managers Checklist | GDL-EPPM019 |
| Domain: | Category: |
| Business | Work Plan Standard / Project Checklists |
| Date Issued: | Issued By: |
| 12/19/2002 | DHS Bureau of Information Systems |
| Date Reviewed: |  |
| 03/10/2016 |  |

General:

This checklist provides a list of the detailed roles and responsibilities needed in Implementation Manager’s Checklist.

The purpose of this document is to track the appropriate Implementation Manager’s requirements.

Guideline:

Implementation Manager Roles & Responsibilities

#### Prior to Implementation Day

- Start involvement with project team and familiarize with project timelines and functionality

- Verify all implementation checklists have been completed and filed

- Gather information on impact analysis to other systems or scheduled tasks during migration time period

- Finalize and maintain implementation plan

- Coordinate rollout status meetings for time period prior to implementation

- Coordinate walk-through meetings to secure stakeholder sign-off of deliverables

- Create contingency plan(s)

- Execute communication plan within team and across teams

- Daily updates to team and management before implementation

- Identify backup resource for every role

- Maintain all contact information for team members and back-up team

- Determine short term post-implementation maintenance resources

- Coordinate testing team members and plan for post-implementation testing

#### On Implementation Day

  - Implementation Manager shall have no direct responsibility for any implementation tasks

  - Coordinate times of arrival with team

  - Distribute Implementation Plan to team

  - Solicit status throughout implementation tasks and disseminate to other team members affected by tasks

  - Provide single point of contact for implementation team

  - Manage communication plan during implementation

  - Obtain any additional resources or information needed to complete implementation tasks

  - Responsible for organizing and securing final go/no go decisions from stakeholders

  - Provide logistics support to team (i.e. meals)

  - Declare implementation complete or provide a plan for remaining task completion after scheduled implementation timeframe

#### Post Implementation

- Facilitate phase exit review with team and stakeholders

- Provide minutes of action items and lessons learned for future implementations to Project Management Team for inclusion in central implementation guideline

- Transfer knowledge to implementation manager of next rollout if applicable

- Ensure post-implementation short term resources are available for immediate fixes or post-implementation clean-up tasks

- Organize and Conduct Recognition Event

Implementation Manager’s Checklist

Project Name: ______________________________________________________

Target Production Machine: ___________________________________________

|  | Checkpoint | Completed Date |
| --- | --- | --- |
| 1 | Before Implementation |  |
| A | Verify all implementation checklists are completed and filed |  |
| B | Assemble Team Contact information |  |
| C | Finalize Implementation Plan |  |
| D | Identify Backup Resources for Every Shift Resource |  |
| E | Finalize Contingency Plan |  |
| F | Finalize post-implementation resource testing plan |  |
| 2 | On Implementation Day |  |
| A | Declare implementation complete and schedule phase exit review |  |
| B | Provide a plan to resolve action items resulting from phase exit review |  |
| 3 | After Implementation |  |
| A | Ensure completion of all action item plans from phase exit review |  |
| B | Update implementation guidelines |  |

Refresh Schedule:

All guidelines and referenced documentation identified in this standard will be subject to review and possible revision annually or upon request by the DHS Information Technology Standards Team.

Guideline Revision Log:

| Change Date | Version | Change Description | Author and Organization |
| --- | --- | --- | --- |
| 12/19/2002 | 1.0 | Initial creation. | Momentum |
| 04/04/2003 | 1.0 | Comply with DPW Standards | DCSS – Process Section |
| 02/15/2005 | 1.0 | Reviewed content – No changes | DCSS-Process Section |
| 01/05/2007 | 1.0 | Reviewed content – No changes | PMO-DCSS |
| 09/12/2008 | 1.1 | Reviewed content & edited style | EPPM |
| 12/20/2010 | 1.2 | Reviewed content – No changes | EPPM |
| 04/28/2015 | 1.3 | Changed DPW to DHS | BIS/DEPPM |
| 03/10/2016 | 1.3 | Annual Review | BIS/DEPPM |