COMMONWEALTH OF PENNSYLVANIA

DEPARTMENT OF HUMAN SERVICES

INFORMATION TECHNOLOGY GUIDELINE

| Name Of Guideline: | Number: |
| --- | --- |
| In-Phase Assessment Process Guide | GDL-EPPM003 |
| Domain: | Category: |
| Business | Guidelines |
| Date Issued: | Issued By: |
| 03/01/1999 | DHS Bureau of Information Systems |
| Date Revised: |  |
| 03/29/2016 |  |

Table of Contents

Introduction	5

Purpose	5

1.0 Overview	5

Who Conducts	5

Applicability	5

Timing/Frequency	5

Diagram	6

In-Phase IPA	6

End of Phase IPA	6

Process Ownership	6

Change Control	7

Relationship to Other System Development Processes	7

Process Measurements	7

2.0 Process	7

Scope	7

Stakeholders	8

Inputs	8

IPA Process Flow	9

Plan IPAs	9

Schedule Review	9

Receive Deliverables	10

Conduct Review	10

Review Levels	10

Prepare Review Findings	10

Process Output	10

Responsibility Matrix	12

3.0 Review Guide	13

Guidance	13

3.1 Reviewer Selection	13

3.2 SDM Deliverables Review Guidance	13

Description	13

Guidance	14

System Development Deliverables Review Level Table	16

3.2.1 Project Plan	18

3.2.2 Structured Walkthrough (documentation) (level 2)	18

3.2.3 Quality Management Plan (level 3)	19

3.2.3 Feasibility Study (level 2)	19

3.2.5 Change Management Plan (level 3)	19

3.2.6 Requirements Traceability Matrix (level 2)	19

3.2.7 Requirements Definition Document (RDD) Process Model Narratives (level 3)	20

3.2.8 Disaster Recovery Plan (level 2)	20

3.2.9 RDD Data Dictionary (level 2)	20

3.2.10 RDD Logical Data Model (level 2)	20

3.2.11 Requirements Definition Document (RDD) (level 2)	20

3.2.12 Test Plan (level 3)	21

3.2.13 General System Design Document (level 3)	21

3.2.14 GSD User Interface (level 3)	22

3.2.15 GSD Data Dictionary (level 3)	22

3.2.16 GSD Logical Data Model (level 3)	22

3.2.17 Requirements Traceability Matrix (expanded) (level 2)	23

3.2.18 System Architecture Document (level 3)	23

3.2.19 Capacity Plan (initial) (level 2)	23

3.2.20 Training Plan (level 2)	23

3.2.21 Conversion Plan (level 2)	24

3.2.22 Detailed System Design (DSD) Document (level 3)	24

3.2.23 DSD Data Dictionary (level 3)	24

3.2.24 Physical Data Model (level 3)	24

3.2.25 Requirements Traceability Matrix (expanded) (level 2)	24

3.2.26 Test Plan (revised) (level 3)	24

3.2.27 Conversion Plan (revised) (level 3)	25

3.2.28 Electronic Commerce Security Assessment (ECSA) Document (level 3)	25

3.2.29 Application Code (level 2)	25

3.2.30 Test Plan (final) (level 3)	26

3.2.31 Requirements Traceability Matrix (expanded) (level 2)	26

3.2.32 Test Scenarios (level 2)	26

3.2.33 Operating Documentation (level 2)	27

3.2.34 Training Plan (revised) (level 2)	27

3.2.35 Capacity Plan (final) (level 3)	28

3.2.36 Batch Operations Manual (BOM) (level 2)	28

3.2.37 Batch Operations Services Request (level 2)	28

3.2.38 Test Reports (System and Integration Test) (level 2)	29

3.2.39 Test Reports (Load Test) (level 2)	29

3.2.40 Test Reports (Regression Test) (level 2)	29

3.2.41 Test Report (Acceptance Test) (level 2)	29

3.2.42 Requirements Traceability Matrix (final) (level 3)	29

3.2.43 Operating Documentation (revised) (level 2)	29

3.2.44 Training Plan (final) (level 3)	30

3.2.45 Deployment Playbook (level 3)	30

3.2.46 Installation Test Materials (level 2)	30

3.2.47 Training Materials (level 3)	30

3.2.48 Conversion Plan (level 3)	30

3.3 Project Management Review Guidance	31

Description	31

Guidance	31

Project Management Review Level Table	32

3.3.1 Project Objectives Summary (level 1)	33

3.3.2 Development Approach (level 3)	33

3.3.3 Project Management Team (level 3)	33

3.3.4 Roles/Responsibilities (level 2)	33

3.3.5 Problem Escalation (level 1)	33

3.3.6 Assumptions/Constraints/Dependencies (level 3)	34

3.3.7 Estimates (level 3)	34

3.3.8 Phase/Project Schedule (level 3)	34

3.3.9 Status Reporting (level 3)	35

3.3.10 Resource Planning (level 3)	35

3.3.11 Budget - Plan versus Actual (level 2)	35

3.3.12 Sign-Offs (prior phase exit) (level 1)	36

3.3.13 Change Management (level 2)	36

3.3.13.1 Baseline Identification (level 2)	36

3.3.13.2 Change Initiation (level 3)	36

3.3.13.3 Change Evaluation (level 3)	37

3.3.13.4 Change Approval (level 3)	37

3.3.13.5 Auditing (level 2)	37

3.3.13.6 Change Control Log (level 2)	37

3.3.13.7 Re-baseline Requirements (level 2)	37

Appendix A	38

Refresh Schedule	39

Guideline Revision Log	39

In-Phase Assessment Process Guide

Introduction

In-Phase Assessments (IPAs) are independent reviews of system development and maintenance projects.  IPAs are conducted in all phases of the software development lifecycle (SDLC) and maintenance phases in accordance with the IPA schedule, which is documented in the project plan.  This document defines the process for planning and conducting IPAs.

Purpose

The purpose of IPAs is to ensure, via an independent assessment, the established system development and project management processes and procedures are being followed effectively, and the exposures and risks to the current project plan are identified and addressed.

An IPA is a project review conducted by a reviewer independent of the project.  The reviewer assesses a project's processes, outputs, and deliverables to verify adherence to standards and sound system development and project management practices are being followed.  An IPA is a paper review and does not require meetings among the involved parties.

1.0 Overview

Who Conducts

Within the current framework of deployment of this process, the Project Management Team will conduct the IPAs.

Applicability

This process is applicable to all Department of Human Services (DHS) development and maintenance efforts following the DHS Software Development Methodology (SDM).

Timing/Frequency

An IPA can be conducted anytime during a phase whenever a deliverable is stable enough, or near the end of a phase to prepare for a phase exit.

Diagram

The following diagram shows the timing of IPAs relative to the SDM lifecycle. The break out of the IPAs shown in the planning phase also would apply to the other SDLC phases.

IPA

IPA

Phase exit (this is a separate process)

| ###### Planning |  |  | ###### Requirements ###### Definition |  |  | ###### General ###### System ###### Design |  |  | ###### Detailed ###### System ###### Design |  |  | ###### Development |  |  | ###### Software ###### Integration ###### & Testing |  |  | ###### Acceptance ###### & ###### Installation |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

In-Phase IPA

One or more in-phase IPAs can be scheduled for a given phase. The purpose of this review is to assess one or more deliverables when development (of the deliverable) is far enough along to allow for review, and early enough to allow for revisions prior to phase exit. The results of the review are contained in a report submitted directly to the project manager.

End of Phase IPA

An end-of-phase IPA must be conducted near the end of each phase.  The purpose of this review is to assess the readiness of a project to proceed to the next phase by reviewing all the deliverables for the current phase.  The results of this review are contained in a report submitted to the project manager.  Copies of the report may be provided to the project sponsor, as appropriate.  In order to exit the current phase, the project manager must develop an acceptable action plan to address any open issues or qualifications.

Process Ownership

The responsibilities of the IPA process include the project sponsor approving the initial process definition document and changes during process improvement.  The responsibilities of the process include initial process definition, process implementation, and conducting ongoing process improvement.

Change Control

The IPA process is a component of the SDM.  Changes to this process will be instituted using the same change mechanism implemented to process changes to the SDM.

Relationship to Other System Development Processes

The IPA process is a primary component of the SDM.  Together with other processes it serves to ensure a consistent and predictable outcome in the resulting software.  The IPA process is complementary to other processes such as Phase Exits and Structured Walkthroughs.

Process Measurements

Process measurements are required in order to understand, in a quantifiable manner, the effectiveness of a process at work.  If measurements indicate the process is not working as designed, a causal analysis is conducted to identify the root cause of the breakdown, and changes should be implemented via the Program Management Office.  The IPA process is considered to be effective (working as designed) if:

- All issues to be resolved in the current phase are identified

- Unmet project objectives can be attributed to issues documented in an IPA

- All issues without an acceptable action plan become qualifications to exit the current phase

- All issues are properly documented and maintained in the Project Folder

Specific procedures for capturing the data for the above measurements will be defined during process improvement.

2.0 Process

Scope

The IPA process begins with the scheduling of the review and ends with the delivery of the report produced after the review.

It is the responsibility of the project manager to develop and implement solutions for the issues and qualifications documented during the review.  The project manager must develop an appropriate action plan for each issue.

Stakeholders

The stakeholders of the IPA process are those individuals or organizations using the output of the IPA process.  The primary stakeholders of the process are:

- Project manager

- Project manager's manager

- Quality Assurance (QA)

Secondary customers of the process are:

- Project sponsor

- Users

The project management team produces outputs and deliverables which become input to the IPA process.

Inputs

The following are the minimum inputs to the IPA process:

- Software development lifecycle deliverable(s)

- Project Plan developed during the planning phase, which includes the work breakdown structure and timeline in addition to other components

- Updated Project Plan revised during all subsequent phases

- Structured walkthrough minutes

IPA Process Flow

The following chart depicts the IPA process flow:

| ###### Planning Phase |  |
| --- | --- |
| Plan for the review | - IPA target dates defined in the project plan for each phase |
| ###### All Other Phases |  |
| Schedule the Review | - Set date - Secure agreement(s) |
| Receive Deliverables | - Phase deliverables - Updated project plan - Walkthrough minutes - Other applicable items |
| Conduct the Review | - Review project plan - Review other items - Review deliverables - Formulate assessment |
| Prepare Review Findings | - Assessment of risk to achieve plan - List of concerns - Recommendations |

Discuss review findings with the project manager.

Plan IPAs

In the planning phase, the target date for conducting the IPAs at each phase is documented in the project plan.  In-phase IPAs can be conducted at any logical point in the phase.  End-of-phase IPAs should be scheduled near the end of a phase (e.g., 2 or 3 weeks ahead of the phase exit milestone).  In-phase IPAs are scheduled for the next phase only, since reviews for all subsequent phases might be difficult to plan in advance.

Schedule Review

In each phase, as soon as practical, the actual assessment point is to be established and agreed-to, and the activity scheduled so the project manager is aware and there are no surprises.

Receive Deliverables

The reviewer is provided a copy of the deliverables to be reviewed, plus the current project plan if it is an end-of-phase IPA.  The deliverables will vary according to the project's phase of development.  Detailed review guidance is provided in 3.2 System Development Deliverables Review Level Table.

Conduct Review

The reviewer should examine each deliverable.  The depth of the examination will vary according to the deliverable and the project's phase of development.  Guidance to assist the reviewer is provided in 3.0 Review Guide.

Review Levels

The following are the levels of review performed on the SDM deliverables.  For each deliverable, specific guidance is provided in 3.0 Review Guide.

| ###### Level | ###### Explanation |
| --- | --- |
| 1 | - Verify the existence of the work product or deliverable - Review to ensure the work product or deliverable exists and is complete |
| 2 | - Verify minimum content exists. - Review to ensure the minimum level of information has been provided. - Verify the existence of content by checking sections/headings. |
| 3 | - Verify content is rational. - Review to make judgments as to the quality and validity of the deliverable |

Prepare Review Findings

The reviewer documents the results of the IPA and produces the report described in the Process Output section.

Process Output

A report must be produced when the IPA process is executed.  Each IPA requires a report even if no issues were identified during the review.  The report should be brief with the focus on providing a clear statement of the issues(s); solutions may be suggested, but are the project manager's responsibility.  The report includes:

- A written assessment of the current project plan in terms of the following:

- Risk to schedule and budget

- Risk for next phase

- Risk for remainder of project

Risk categories:

- Low - Potential or existing problems must be addressed to avoid an impact to the current project plan.  This would also apply if no issues were identified.

- Medium - Problems exist that have a high probability of impacting the current project plan or other dependencies.

- High - Serious problems exist (without an acceptable plan to resolve) that have a high probability of impacting user acceptance, the current project plan, or other dependencies.

- Lists of issues/concerns if any were formed during the review.  An issue is logged if there is a problem without a visible plan for resolution.  Once a list of issues has been compiled, it is reviewed with the project manager to see if any new or additional information might mitigate or eliminate any of them.  Remaining issues must be addressed with an action plan from the project manager.  Issues from an end-of-phase IPA might become "qualifications" to exiting the current phase.  Refer to the Phase Exit Process Guide for additional information.

Examples of issues:

- No description of the estimating methodology used

- No definition of a change control mechanism

- Signoff (go/no go) from the prior phase is not visible

- Concern about the appropriateness of the process used to arrive at technical decisions.  In this example, the reviewer may recommend an additional in-depth review by technical experts as an action item.

If no issues were identified, the report only needs to contain the name of the project, date of the review, reviewer name, and a statement that no issues were identified.

- Additional reviewer comments, as appropriate. These include suggestions and recommendations benefiting the project.  The reviewer is encouraged to provide this feedback based on his/her experience.  Reviewer comments are provided for the benefit of the project manager and not logged as issues requiring an action plan.  In certain cases the reviewer may also recommend a more in-depth review by an individual highly skilled in a certain area, to help validate technical decisions and conclusions.

For in-phase IPAs, the ISA Report (Appendix A) is distributed to:

- Project manager

For end-of-phase IPAs, the ISA Report (Appendix A) is distributed to:

- Project manager, with copies to:

- Project sponsor

- Quality Assurance manager

Responsibility Matrix

The following matrix defines the responsibilities for the various organizations involved in the IPA process.

|  | ###### Project Management Team | ###### Quality Assurance | ###### IPA Reviewer (1) |
| --- | --- | --- | --- |
| Prepare Deliverables | P |  |  |
| Schedule IPA | P | R |  |
| Conduct IPA | S | P |  |
| Compile list of issues | R | P |  |
| Prepare assessment |  | P |  |
| Ensure issue resolution | P |  |  |
| Monitor process effectiveness |  | P |  |
| Continuous process improvement | S | P |  |

Legend

P=Perform	    R=Review     S=Support

(1) As the process is currently implemented, the IPA is conducted by Quality Assurance.  However, it is possible for the IPA to be conducted by other parties, e.g. a peer project manager.  A description of the skills required to conduct IPAs is provided in 3.1 Reviewer Selection.

3.0 Review Guide

This section contains guidance on selecting an IPA reviewer, the appropriate level of review to be performed for each deliverable (or output), and what to look for in each.  Some deliverables are prepared once during the applicable phase, others are subsequently updated as the project progresses.  These variances are highlighted in the review level tables.

Guidance

The following guidance is provided in this section.

- 3.1 Reviewer Selection

- 3.2 Deliverables Review Guidance

- 3.3 Project Management Review Guidance

3.1 Reviewer Selection

The review must be conducted by a person who does not report to the same organization as the development or maintenance team.  This allows for an independent view of problems and issues existing and serves as a cross-training tool.  The experience and skills required include:

- Hands-on experience planning and managing technically complex software development projects

- Working knowledge of the Software Development Methodology (SDM)

- Ability to deal with people and communicate well

Individuals who typically have the technical background, experience, and skills required include team managers, project managers, project leaders, task leaders, quality assurance representatives.

3.2 SDM Deliverables Review Guidance

Description

This section provides guidance on what to look for when reviewing and assessing the various SDLC deliverables and components of the project plan. Outputs (deliverables) are produced throughout the SDLC.  They serve to document all project related data and form the basis of understanding between all parties involved in developing systems.  These deliverables are required at various phases of the SDLC.

For a detailed description of the SDLC deliverables refer to the SDM.

Guidance

The review guidance for the following deliverables is provided in this section.

- 3.2.1 Project Plan

- 3.2.2 Structured Walkthrough

- 3.2.3 Quality Management Plan

- 3.2.4 Feasibility Study

- 3.2.5 Change Management Plan

- 3.2.6 Requirements Traceability Matrix

- 3.2.7 Requirements Definition Document (RDD) Process Model Narratives

- 3.2.8 Disaster Recovery Plan

- 3.2.9 RDD Data Dictionary

- 3.2.10 RDD Logical Model

- 3.2.11 Requirements Definition Document (RDD)

- 3.2.12 Test Plan

- 3.2.13 General System Design Document

- 3.2.14 GSD User Interface

- 3.2.15 GSD Data Dictionary

- 3.2.16 GSD Logical Data Model

- 3.2.17 Requirements Traceability Matrix (expanded)

- 3.2.18 System Architecture Document

- 3.2.19 Capacity Plan (initial)

- 3.2.20 Training Plan

- 3.2.21 Conversion Plan (initial)

- 3.2.22 Detailed System Design (DSD) Document

- 3.2.23 DSD Data Dictionary

- 3.2.24 DSD Physical Data Model

- 3.2.25 Requirements Traceability Matrix (expanded)

- 3.2.26 Test Plan (revised)

- 3.2.27 Conversion Plan

- 3.2.28 Electronic Commerce Security Assessment (ECSA) Document

- 3.2.29 Application Code

- 3.2.30 Test Plan (final)

- 3.2.31 Requirements Traceability Matrix (expanded)

- 3.2.32 Test Scenarios

- 3.2.33 Operating Documentation

- 3.2.34 Training Plan

- 3.2.35 Capacity Plan (final)

- 3.2.36 Batch Operations Manual (BOM)

- 3.2.37 Batch Operations Services Request

- 3.2.38 Test Report (System and Integration Test)

- 3.2.39 Test Report (Load Test)

- 3.2.40 Test Report (Regression Test)

- 3.2.41 Test Report (Acceptance Test)

- 3.2.42 Requirements Traceability Matrix (final)

- 3.2.43 Operating Documentation (revised)

- 3.2.44 Training Plan (final)

- 3.2.45 Deployment Book

- 3.2.46 Installation Test Materials

- 3.2.47 Training Materials

- 3.2.48 Conversion Plan

The table on the following page identifies the appropriate level of review to be performed depending on the deliverable and the phase of development.

System Development Deliverables Review Level Table

| ###### Table Legend | ###### SDM Deliverable | ###### SDM Phase |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ###### Planning | ###### Requirements Definition | ###### General System Design | ###### Detailed System Design | ###### Development | ###### Software Integration & Testing | ###### Acceptance & Installation |
| Review Levels: -1- Verify the existence of the deliverable -2- Verify minimum content exists -3- Verify content is rational (1) See Project Management Review Level table for details | Project Plan (1) | 3 | 3 | 3 | 3 | 3 | 3 | 3 |
|  | Structured Walkthrough | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
|  | Quality Management Plan | 3 |  |  |  |  |  |  |
|  | Feasibility Study | 2 |  |  |  |  |  |  |
|  | Change Management Plan | 3 |  |  |  |  |  |  |
|  | Requirements Traceability Matrix (draft) |  | 2 |  |  |  |  |  |
|  | Requirements Definition Document (RDD) Process Model Narratives |  | 3 |  |  |  |  |  |
|  | Disaster Recovery Plan |  | 2 |  |  |  |  |  |
|  | RDD Data Dictionary |  | 2 |  |  |  |  |  |
|  | RDD Logical Data Model |  | 2 |  |  |  |  |  |
|  | Requirements Definition Document |  | 2 |  |  |  |  |  |
|  | Test Plan |  | 3 |  |  |  |  |  |
|  | General System Design (GSD) Document |  |  | 3 |  |  |  |  |
|  | GSD User Interface |  |  | 3 |  |  |  |  |
|  | GSD Data Dictionary |  |  | 3 |  |  |  |  |
|  | GSD Logical Data Model |  |  | 3 |  |  |  |  |
|  | Requirements Traceability Matrix (expanded) |  |  | 2 |  |  |  |  |
|  | System Architecture Document |  |  | 3 |  |  |  |  |
|  | Capacity Plan (initial) |  |  | 2 |  |  |  |  |
| ###### Table Legend | ###### SDM Deliverable | ###### SDM Phase |  |  |  |  |  |  |
|  |  | ###### Planning | ###### Requirements Definition | ###### General System Design | ###### Detailed System Design | ###### Development | ###### Software Integration & Testing | ###### Acceptance & Installation |
| Review Levels: -1- Verify the existence of the deliverable -2- Verify minimum content exists -3- Verify content is rational (1) See Project Management Review Level table for details | Training Plan |  |  | 2 |  |  |  |  |
|  | Conversion Plan (initial) |  |  | 2 |  |  |  |  |
|  | Detailed System Design (DSD) Document |  |  |  | 3 |  |  |  |
|  | DSD Data Dictionary |  |  |  | 3 |  |  |  |
|  | DSD Physical Data Model |  |  |  | 3 |  |  |  |
|  | Requirements Traceability Matrix (expanded) |  |  |  | 2 |  |  |  |
|  | Test Plan (revised) |  |  |  | 3 |  |  |  |
|  | Conversion Plan (revised) |  |  |  | 3 |  |  |  |
|  | Electronic Commerce Security Assessment (ECSA) Document |  |  |  | 3 |  |  |  |
|  | Application Code |  |  |  |  | 2 |  |  |
|  | Test Plan (final) |  |  |  |  | 3 |  |  |
|  | Requirements Traceability Matrix (expanded) |  |  |  |  | 2 |  |  |
|  | Test Scenarios |  |  |  |  | 2 |  |  |
|  | Operating Documentation |  |  |  |  | 2 |  |  |
|  | Training Plan (revised) |  |  |  |  | 2 |  |  |
|  | Capacity Plan (final) |  |  |  |  | 3 |  |  |
|  | Batch Operations Manual (BOM) |  |  |  |  | 2 |  |  |
|  | Batch Operations Services Request |  |  |  |  | 2 |  |  |
| ###### Table Legend | ###### SDM Deliverable | ###### SDM Phase |  |  |  |  |  |  |
|  |  | ###### Planning | ###### Requirements Definition | ###### General System Design | ###### Detailed System Design | ###### Development | ###### Software Integration & Testing | ###### Acceptance & Installation |
| Review Levels: -1- Verify the existence of the deliverable -2- Verify minimum content exists -3- Verify content is rational (1) See Project Management Review Level table for details | Test Report (System and Integration Test) |  |  |  |  |  | 2 |  |
|  | Test Report (Load Test) |  |  |  |  |  | 2 |  |
|  | Test Report (Regression Test) |  |  |  |  |  | 2 |  |
|  | Test Report (Acceptance Test) |  |  |  |  |  | 2 |  |
|  | Requirements Traceability Matrix (final) |  |  |  |  |  | 3 |  |
|  | Operating Documentation (revised) |  |  |  |  |  | 2 |  |
|  | Training Plan (final) |  |  |  |  |  | 3 |  |
|  | Deployment Playbook |  |  |  |  |  |  | 3 |
|  | Installation Test Materials |  |  |  |  |  |  | 2 |
|  | Training Materials |  |  |  |  |  |  | 3 |
|  | Conversion Plan |  |  |  |  |  |  | 3 |

3.2.1 Project Plan

Project plan guidance is provided in 3.3 Project Management Review Guidance.

3.2.2 Structured Walkthrough (documentation) (level 2)

The structured walkthrough (i.e. the documented results of the walkthrough), including the Management Summary and any other associated available documentation, must contain a list of any defects identified during the walkthrough, and a clear disposition for each defect.  The reviewer's objective is to verify:

- One or more structured walkthroughs were conducted depending on the phase of development in accordance with SDM guidelines

- All defects have been addressed and closed; no action item has been left open-ended

- If a follow-up structured walkthrough was required, the walkthrough was conducted and all action items were addressed

3.2.3 Quality Management Plan (level 3)

The Quality Management Plan clearly defines the project's quality management policies and procedures. The plan addresses:

- When In-Phase assessments will be conducted and by whom

- Applicability of published standards and procedures

- Monitoring for application of applicable standards and procedures

- Assurance of resolution of discrepancies

- Assessment of project progress

- Assuring the integrity of the software

3.2.3 Feasibility Study (level 2)

The feasibility study is reviewed to determine if the following elements have been identified:

- Project objectives

- System automation alternatives

- Potential technical solutions

- Benefits and costs

- Recommendations

The project file is reviewed to verify a structured walkthrough was conducted and any action items resulting from the walkthrough were addressed or resolved.

3.2.5 Change Management Plan (level 3)

Change Management guidance is provided in 3.3 Project Management Review Guidance.

3.2.6 Requirements Traceability Matrix (level 2)

Each requirement must be traceable to one or more design entities.  The matrix is examined to ensure it allows for the design entities to be traced back to the project requirements, and for verification that all requirements are satisfied by the design.

3.2.7 Requirements Definition Document (RDD) Process Model Narratives (level 3)

The requirements definition document is reviewed (use random sampling as appropriate) to ensure it includes:

- Project objectives are consistent with the objectives identified in the management plan

- Requirements exhibit good attributes including clarity (no ambiguity), statement of a business problem or need (not the solution), and sufficient detail to allow for testing

3.2.8 Disaster Recovery Plan (level 2)

The disaster recovery plan is reviewed to determine if it includes:

- Requirements for continuity of operation (COOP), such as data backup, data recovery, and operation startup

- Plans for backup and recovery operations

- Training requirements and plans so the required skills will be in place to execute backup and recovery operations

3.2.9 RDD Data Dictionary (level 2)

The data dictionary (data model) is reviewed to ensure the data elements are documented in detail to include attributes, known constraints, input sources, output destinations, and known formats. The data dictionary must include business rules and cross-referencing information.

The reviewer ensures all data elements have been identified up to this point.

3.2.10 RDD Logical Data Model (level 2)

The RDD logical model is reviewed to ensure it includes:

- Description of the final sources and destination of data

- Description of the net transfer of data across the system boundary

- Complete picture of the system processes, data flow, and data stores

3.2.11 Requirements Definition Document (RDD) (level 2)

The RDD is reviewed to ensure it includes:

- The logical requirements and data requirements without dictating a physical design or technical solutions

- The requirements in non-technical language understandable by the project sponsor and users

- The requirements are organized into meaningful groupings

- A numbering scheme was developed for the unique identification of each requirement

- A method was selected for:

- Tracing the requirements back to the sources of information (Requirements Traceability Matrix)

- Threading requirements through all subsequent lifecycle activities

3.2.12 Test Plan (level 3)

This document is reviewed to ensure it includes: (System Test plan details should be provided in the Detailed System Design Phase)

- Approach to testing (e.g. "...system testing will be conducted by an independent group...")

- Purpose and scope of test efforts to be conducted

- List of items planned to be tested, and items not to be tested

- Rationale for not testing (what is not going to be tested)

- Who (organization) will be responsible for conducting the testing

- Which levels of testing are planned to be conducted (e.g. unit, integration, system, and acceptance)

- Physical location(s) where testing is planned to be conducted

- List of known requirements for conducting testing activities (e.g. hardware, software, skills, space, and equipment)

- Who is expected to sign-off and approve the tests

3.2.13 General System Design Document (level 3)

The General System Design Document is reviewed to ensure it describes the functions of the system in user terminology.  It is to be written from the user/project sponsor’s perspective.  It enables the owner/users to understand how the design will satisfy the requirements, providing an opportunity to give feedback before the design is completed.

The reviewer ensures the general design related outputs have also been documented:

- The design alternatives including evaluation criteria, alternative descriptions, and recommendations

- The operating environment including hardware, software, communications, and interfaces

- System design demonstrating the system architecture, system inputs, outputs, interfaces, and end-user interfaces

- Design method used, design entities, and design dependencies

- Security and control measures to be incorporated into the software system

- The display conventions to be followed for the design of all end-user interfaces (such as application screens)

- The naming and identification conventions for programs, libraries, data bases, tables, and files

- The implementation approach, reflecting the necessary planning to take the system through to implementation

3.2.14 GSD User Interface (level 3)

The user interface is reviewed to ensure the design is appropriate for the users, content, and operating environment of software.

3.2.15 GSD Data Dictionary (level 3)

The data dictionary (data model) is expanded from the Requirements Definition Phase and reviewed to ensure the data elements are documented in detail to include attributes, known constraints, input sources, output destinations, and known formats. The data dictionary must include business rules and cross-referencing information.

Complete data definitions demonstrate:

- The data needs are associated with various system features

- The  data needs match with the data dictionary

- The data dictionary match with specific data structures

- Data record layouts are created

- All data can be maintained through add, change, or delete functions

The data dictionary will be further refined in the Detailed System Design (DSD) Phase to complete the information on data elements, entities, files, physical characteristics, and data conversion requirements.

3.2.16 GSD Logical Data Model (level 3)

The GSD logical model is expanded from the Requirements Definition Phase and reviewed to ensure it includes:

- Description of the final sources and destination of data

- Description of the net transfer of data across the system boundary

- Complete picture of the system processes, data flow, and data stores

3.2.17 Requirements Traceability Matrix (expanded) (level 2)

The Requirements Traceability Matrix developed in the Requirements Definition Phase is expanded (i.e., the GSD ID column B filled out) to relate the GSD to the requirements.  Ensure all required functionality is included in the expanded matrix.

3.2.18 System Architecture Document (level 3)

The System Architecture Document is reviewed to ensure it provides the design and layout of the requirements specific to the system application as a whole (coding standards, application framework usage).

3.2.19 Capacity Plan (initial) (level 2)

The Capacity Plan is reviewed to ensure it includes:

- Estimates for application usage

- Estimates for network bandwidth

- Estimates for disk storage capacity

- Demographic profile environment

- Load test environment

- Production environment

- Batch/File Transfer Protocol (FTP)

3.2.20 Training Plan (level 2)

This document is reviewed to determine if it includes the level of detail needed for training staff to begin logistical training arrangements.  A "draft" level document is not intended to provide complete training plan information.  The training plan includes:

- Background - system description, objectives, curriculum overview

- Training requirements - environment, audience, category, skill level of users

- Objective - expected results of the training in terms of the increased level of user knowledge

- Training strategy - type of training, schedule, duration, sites

- Training resources - resources required, responsibilities of involved parties

- Environment - facilities, support from other groups, equipment, actions required

- Training materials - types of materials required, e.g., system reference manual

3.2.21 Conversion Plan (level 2)

The conversion plan addresses the process of transitioning from the existing manual or automated process to the new application or system.  This plan is reviewed to ensure it includes:

- General information (This section describes, in a concise manner, relevant information about the system and task)

- Data conversion (This section describes the strategy and specific activities required to convert data from the old system to the new one)

3.2.22 Detailed System Design (DSD) Document (level 3)

The Detailed System Design Document is reviewed to ascertain whether it translates requirements into precise specifications of the software components, interfaces, and data which are necessary before coding and testing can begin.  The sequence and conditions inherent within modules should be documented.

3.2.23 DSD Data Dictionary (level 3)

The data dictionary is reviewed and updated to complete the detailed information on data elements, entities, files, physical characteristics, and data conversion requirements.

3.2.24 Physical Data Model (level 3)

The physical data model is reviewed to determine if it includes the following attributes and components:

- Contents and organization of the physical data files

- Processes and data flows among the files

- Modules or groups of modules structured into a hierarchy of sub-systems

- Manual tasks with physical input or output characteristics

3.2.25 Requirements Traceability Matrix (expanded) (level 2)

The requirements traceability matrix is updated and allows for each requirement to be traced to one or more of the detailed design entities to verify all of the requirements will be satisfied by the detailed system design.

3.2.26 Test Plan (revised) (level 3)

The test plan is revised to develop the Integration and System Test plan information.  This document (or section) is reviewed to ensure an incremental integration and test plan exists.  It includes:

- Purpose and scope of test efforts to be conducted

- List of items to be tested, and items not to be tested

- Rationale for not testing what is not going to be tested

- Responsible individual (or organization) for each activity including sign-offs, management, and acceptance

- Schedules

- Description of "how" the testing will be conducted

3.2.27 Conversion Plan (revised) (level 3)

The revised conversion plan further addresses the process of transitioning from the existing manual or automated process to the new application or system.  This plan is reviewed to ensure it includes:

- How the conversions are to be implemented

- How the conversion process is to be tested

- The conversion schedule

- Reports detailing the rejected data as a result of the data cleansing/purification procedure, when appropriate

3.2.28 Electronic Commerce Security Assessment (ECSA) Document (level 3)

The ECSA addresses the appropriate level of security necessary for sending, receiving, and processing electronic transactions.  The ESCA document is reviewed to ensure it includes:

- A structured and consistent method for making such determinations

- Guidance regarding the level of security designed into e-government applications

- Compliance with the Department Standards

- Compliance with the Pennsylvania Electronic Transactions Act

3.2.29 Application Code (level 2)

This deliverable may consist of one or more documents.  The specifications are reviewed to ensure inclusion of:

- Program design characteristics including program architecture, and software and common program features

- Standards and guidelines governing each program coded for the system

- Program specifications (use sampling as appropriate - good rule of thumb is 15 percent)

Note: This should include a description of the logic and other particulars for each program in the system.

- Completed units and modules of code

- Test materials generated from preliminary testing

3.2.30 Test Plan (final) (level 3)

The Integration and System Test Plan is updated to reflect any changes made to the software design.  This document (or section) is reviewed to ensure an incremental Integration and System Test Plan exists.  It includes:

- Purpose and scope of test efforts to be conducted

- List of items to be tested, and items not to be tested

- Rationale for not testing what is not going to be tested

- Responsible individual (or organization) for each activity including sign-offs, management, and acceptance

- Schedules

- Description of "how" the testing will be conducted

3.2.31 Requirements Traceability Matrix (expanded) (level 2)

The requirements traceability matrix is updated and allows for each requirement to be traced back to the project requirements and the DSD to satisfy all the requirements.

3.2.32 Test Scenarios (level 2)

The test scenarios are reviewed to ensure they are based on the requirements, the General System Design (GSD), and Detailed System Design (DSD) Documents.  The essential information includes:

- Version

- Build number

- Retry

- Test Scenario Number

- Process Number

- Environment

- Test scenario description

- Objective

- Assumptions and constraints

- Test files/test data

3.2.33 Operating Documentation (level 2)

The operating documentation is reviewed for accuracy, completeness, and to allow for both ease of operation and maintenance.  Documentation to be produced:

- Application Developer’s Reference Manual (This document includes the information required to allow the development staff to understand and maintain the system programs, data bases, interfaces, and operating environments)

- System Administration Manual (This document provides information necessary to enable the system administrator to understand and access the system functions required to manage the system)

- Data Base Administration Manual (This manual provides the information necessary to enable the data base administrator (DBA) to understand the logical and physical organization, and the record structure of the system)

- Operations Manual (This manual provides the operations group with a description of the system operation environment and the detailed instructions they need to execute the system functions)

3.2.34 Training Plan (revised) (level 2)

This document is expanded and reviewed to include:

- Identification of personnel to be trained.  A list of trainees is reviewed with the project sponsor and users to ensure all personnel to receive training are identified.

- A definition of the overall approach to training along with required courses and materials.

- Delineation of the scope of the training needed for managers, users, operational and maintenance staff.

- Explanation of how and when training is to be conducted, including instructor qualifications, learning objectives, and mastery or certification requirements (if applicable).

- Identification of any skill areas for certification, if required.

- Establishment of a preliminary schedule for the training courses.  The schedule must reflect training requirements and constraints outside of the project.  It may also include the identification of critical paths in the training schedule such as the period for the software installation and conversion to production status.

- The required courses are defined, including an outline of content and sequence.

- Reference to the organization’s training policy for meeting training needs.

- Steps to ensure managers receive orientation on the training program.

- The training courses prepared at the organizational level are developed and maintained according to Commonwealth and organizational standards.

- A waiver procedure for training the individuals possessing the knowledge and skills required to perform their designated role.

- Methods used for evaluating the effectiveness of the training, such as questionnaires, surveys, and post training evaluations.

- Ensure training records are property maintained.

3.2.35 Capacity Plan (final) (level 3)

The revised Capacity Plan is reviewed to ensure the latest capacity requirements are captured and verified to include:

- Estimates for application usage

- Estimates for network bandwidth

- Estimates for disk storage capacity

- Demographic profile environment

- Load test environment

- Production environment

- Batch/File Transfer Protocol (FTP)

3.2.36 Batch Operations Manual (BOM) (level 2)

The BOM is reviewed to determine if it contains sufficient information and detailed instructions required to access and use the system functions.  For very small systems, a quick reference card may be more appropriate and sufficient.  For larger systems, a reference card may also be provided in addition to the BOM.  The extent of the BOM may also depend on the depth of the online help provided; the lower the level of online help the less extensive the BOM needs to be.  A BOM includes:

- Overview of the system history, background, architecture, and current version

- Complete coverage of all system functions, in a logical order

- Samples of screens and reports (where appropriate to show examples)

- Instructions for installing, configuring, and accessing the system

- Security features including what is accessible to each category of users

- Who to contact for additional information or help

3.2.37 Batch Operations Services Request (level 2)

The Batch Operations Services Request is reviewed to validate the need for the batch request and to see if it may adversely affect the system or other batch job schedules.

3.2.38 Test Reports (System and Integration Test) (level 2)

The files are reviewed to ensure the system and acceptance testing results have been documented.  Any defects found must be corrected according to the established procedures including the process for assigning, handling, and disposition defects.

3.2.39 Test Reports (Load Test) (level 2)

The files are reviewed to ensure the load testing results have been documented.  Any defects found must be corrected according to the established procedures including the processes tested, the number of users simulated, and the type of user behavior being simulated.

3.2.40 Test Reports (Regression Test) (level 2)

The files are reviewed to ensure the regression testing (i.e. re-runs of previous tests) results have been documented.  Regression testing verifies code changes have not adversely impacted existing functionality.  It confirms no additional defects are introduced when repairing defects or adding new functionality to ‘approved’ code.

3.2.41 Test Report (Acceptance Test) (level 2)

The files are reviewed to ensure the acceptance testing includes:

- The timeframe when the test(s) are being planned to be conducted.

- A list of organization(s) from which individuals will conduct the tests (at a minimum, this contains positions and skills required)

- The test cases and scenarios planned to demonstrate the requirements have been satisfied in the new system or application

- A list of, or reference to, requirements the system satisfies

- Required hardware, software, documentation, special environmental or operational requirements, and any other special considerations (e.g., travel).

3.2.42 Requirements Traceability Matrix (final) (level 3)

The requirements traceability matrix is updated and allows for each requirement to be traced back to the project requirements and the test scenarios satisfy all the requirements.

3.2.43 Operating Documentation (revised) (level 2)

The Operating Documentation is updated to include the needs addressed in the System and Integration testing.  The reviewer needs to ensure the entire system turnover activities have been completed, including:

- Execution and completion of the DHS Acceptance process

- If deemed appropriate, interviews with the client to determine satisfaction with requirements met

- Final acceptance turnover meeting (This is often waived or canceled)

- Acceptance checklist(s) completed as per the Acceptance process.

3.2.44 Training Plan (final) (level 3)

The Training Plan is finalized in the System Integration and Testing Phase to ensure its readiness and usage for the Acceptance and Installation Phase.

3.2.45 Deployment Playbook (level 3)

The Installation Activities are captured in the Deployment Playbook.  Review this document to ensure it includes:

- Lists all the activities

- Roles and responsibilities

- Contacts

- Duration times for the complete installation

- Deployment of the application

3.2.46 Installation Test Materials (level 2)

If the software being installed is a modification to an existing system, all remaining functions and code affected by the new software must be tested.  Ensure any problems are documented along with the appropriate corrective action.  Information includes:

- General information relevant to the installation process

- Assumptions and dependencies related to the installation activities

- Strategy and schedule for phasing in the new system and disposing of the old one

3.2.47 Training Materials (level 3)

The training materials are reviewed to ensure content, instruction, and support materials meet the needs of the users.

3.2.48 Conversion Plan (level 3)

A conversion plan for the support and maintenance of the system after turnover to the user(s) or after installation into its intended production environment is documented.  It includes the names of the person(s) and/or organization(s) providing support, a service level agreement, which process will be followed (presumably the DHS SDM) for software maintenance, and any schedules, if appropriate.

3.3 Project Management Review Guidance

Description

Project management includes the set of activities related to planning, organizing, directing, staffing, and controlling available resources to achieve distinct goals and objectives established at the beginning of a project.  The key to successful project management is a good project plan, which is developed initially in the planning phase.  The plan is dynamic, and is reviewed and revised in subsequent phases to reflect approved changes.

Guidance

This section is a reference guide to assessing the various components of a project plan.

Guidance for the deliverables is provided in this section.

- 3.3.1 Project objectives summary

- 3.3.2 Development approach

- 3.3.3 Project management team

- 3.3.4 Roles/responsibilities

- 3.3.5 Problem escalation

- 3.3.6 Assumptions/constraints/dependencies

- 3.3.7 Estimates

- 3.3.8 Phase/project schedule

- 3.3.9 Status reporting

- 3.3.10 Resource planning

- 3.3.11 Budget - plan vs. actual

- 3.3.12 Sign-offs (prior phase exit)

- 3.3.13 Change control management

The following table identifies the appropriate level of review to be performed depending on the project management activity and the phase of development.

Project Management Review Level Table

| ###### Table Legend | ###### Project Plan | ###### SDM Phase |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | ###### Planning | ###### Requirements Definition | ###### General System Design | ###### Detailed System Design | ###### Development | ###### Software Integration & Testing | ###### Acceptance & Installation |
| Review Levels: -1- Verify the existence of the deliverable -2- Verify minimum content exists -3- Verify content is rational | Project objectives summary | 1 |  |  |  |  |  |  |
|  | Development approach | 3 |  |  |  |  |  |  |
|  | Project management team | 3 |  |  | 3 | 3 | 3 |  |
|  | Roles/responsibilities | 2 |  |  | 2 | 2 | 2 |  |
|  | Problem escalation | 1 |  |  |  |  |  |  |
|  | Assumptions/constraints/ dependencies | 3 | 3 | 3 | 3 | 3 | 3 |  |
|  | Estimates | 3 | 3 | 3 | 3 | 3 | 3 |  |
|  | Phase/project schedule | 3 | 3 | 3 | 3 | 3 | 3 |  |
|  | Status reporting | 3 | 1 | 1 | 1 | 1 | 1 |  |
|  | Resource planning | 3 | 1 | 1 | 1 | 1 | 1 |  |
|  | Budget – plan vs. actual | 2 | 2 | 2 | 2 | 2 | 2 |  |
|  | Sign-offs (prior phase exit) |  | 1 | 1 | 1 | 1 | 1 |  |
|  | ###### Change Management |  |  |  |  |  |  |  |
|  | Baseline Identification |  | 2 |  |  |  |  |  |
|  | Change Initiation |  | 3 |  |  |  |  |  |
|  | Change evaluation |  | 3 |  |  |  |  |  |
|  | Change approval |  | 3 |  |  |  |  |  |
|  | Auditing |  |  | 2 | 2 | 2 | 2 | 2 |
|  | Change Control Log |  |  | 3 | 3 | 3 |  |  |
|  | Re-baseline requirements |  |  | 2 | 2 | 2 |  |  |

3.3.1 Project Objectives Summary (level 1)

This section defines the project objectives in summary form.  It is intended to give the reader a high level overview of the project.  It should be in summary form and therefore brief (e.g., one-half page to 2-3 pages).  It can be copied from other project documents where it may already exist.

3.3.2 Development Approach (level 3)

This section defines the development environment in terms of the SDLC methodology for the project.  This section includes:

- The standard for DHS projects is the SDM.

- The variations taken (if any) from the standard development model

- If deviations are taken, what is in place to mitigate the increased risk

- Any feature unique regarding the SDLC or project management aspects of this project.

3.3.3 Project Management Team (level 3)

The project management team section of the project plan is reviewed to ensure the members of the team have been identified, by name, for the next phase of development and, if possible, for the entire project.  The composition of the team should be reviewed and revised as the project progresses through the various phases of development.  This section is reviewed along with the section on schedules and estimates to determine if the two sections support each other.

3.3.4 Roles/Responsibilities (level 2)

The roles and responsibilities of all team members and users are documented initially in the Planning phase.  The information is revised in subsequent lifecycle phases.  If there are changes, they are based on the skills and experience of each individual.

This section should include, at a minimum, the names and organizations of those individuals responsible for providing a go/no go position (sign-off) at phase exit. Typically, this would include the project manager, the project sponsor, the quality assurance representative, and the user.  Other persons having a support or participatory role are also identified if possible.

3.3.5 Problem Escalation (level 1)

All problems are brought to the attention of the project manager first.  Problem management is the instrument used to handle project related conflicts, misunderstandings, and problems not resolved at the project manager level.  This section is reviewed to ensure:

- Escalation point (individual(s) to whom the problem will be brought for resolution if the problem is not resolved at the project manager level.

- Timeframe for a problem to be brought to resolution after it was escalated.

- This could be one day, several days, or week(s).

3.3.6 Assumptions/Constraints/Dependencies (level 3)

This section contains all project-wide assumptions, known constraints, and dependencies identified for this project.  Assumptions and dependencies are very specific.  Generally known or accepted practices usually do not need to be documented.  In many cases, assumptions, constraints, and dependencies will affect project estimates and schedules. This is updated and reviewed at every phase of the SDLC.

An example of a dependency:

- The development team is dependent on the availability of user personnel to review deliverables within ten (10) business days.

An example of an assumption:

- One Application Developer III with 4 years of Visual Basic experience will be on board as planned by March 31, 2005.

3.3.7 Estimates (level 3)

Estimates are reviewed to ensure they include: (In subsequent phases, changes to the original estimates may be documented)

- Description of the methodology or combination of methodologies used to arrive at the estimates (planning phase only)

- Line items for all associated project costs including labor months and other direct costs

- Breakout of project phase activities (This is detailed for the next phase of development and in summary form for the rest of the project.)

- Revisions from the prior phase of development, if there are approved changes increasing or decreasing project cost

- Assumptions upon which the estimates are based

- Factors used to arrive at the contingency numbers

3.3.8 Phase/Project Schedule (level 3)

The project schedule for the next phase is reviewed for evidence of:

- Each activity and its associated data (e.g., start and end dates) can be part of a work breakdown structure also showing relationships.

- Date for the phase exit

- Description of each deliverable or activity.

- Team or Individual (name) responsible for the deliverable or activity

- Projected start and end dates for each activity

- Impact (if any) of approved changes on the schedule (the one approved at the prior phase exit) and the base lining of the new schedule

- Critical path(s) identified and dependencies, if any

- For subsequent phases, at a minimum, milestones (phase exit dates) and SDM deliverables are documented for each phase

3.3.9 Status Reporting (level 3)

Regular, clear, and effective communication is critical to the success of any project.  In the planning phase, this section is reviewed to identify

- Method for reporting project progress and problems

- Frequency of status meetings

- Procedure for tracking action items to closure

In subsequent phases, look for evidence the established reporting practice is being followed.

3.3.10 Resource Planning (level 3)

Resource planning is essential to the success of a project.  It must be started as early as possible in the planning phase and then revised for each subsequent phase of development. It is based on the known project requirements and demonstrates when necessary resources and skills need to be on board.

The following are examples of resources:

- Hardware: OptiPlex GX270, 2.80GHz, Pentium4, 512K Cache, Gigabit

- Software: Oracle Database, Enterprise Edition 800

- Office space: four offices, 12 by 12 feet (each office will accommodate two application developers)

- People: two application developers III, two application developers II, one quality assurance analyst (specify experience requirements)

- Dates: target dates for acquiring specified resources

In subsequent phases, look for evidence that action has been taken to ensure resources will be available when needed.

3.3.11 Budget - Plan versus Actual (level 2)

Review this section to verify it includes:

- Project status from the financial perspective

- Planned/approved expenditure level to date

- Actual expenditure level to date

- The difference (delta) between planned and actual expenditure levels, if any, and to what this difference is attributable

Any changes must be appropriately reflected in the project plan.

3.3.12 Sign-Offs (prior phase exit) (level 1)

The project files contain the sign-offs received at the prior phase exit.  These are from the individuals identified as having sign-off rights in the roles and responsibilities section of the project plan.

3.3.13 Change Management (level 2)

The change management section of the project plan has several important sections to be reviewed including:

- 3.3.13.1 Baseline identification

- 3.3.13.2 Change initiation

- 3.3.13.3 Change evaluation

- 3.3.13.4 Change approval

- 3.3.13.5 Auditing

- 3.3.13.6 Change control log

- 3.3.13.7 Re-baseline requirements

3.3.13.1 Baseline Identification (level 2)

Review this section to verify the baselines have been identified in order to establish control points for various SDLC deliverables.  Required elements include:

- Functional baseline

- Allocated baseline

- Product baseline

3.3.13.2 Change Initiation (level 3)

Review this section to determine if it contains:

- The name and organization of the individual(s) who are authorized to approve requests for change

- The form(s) on which the change request must be submitted (Quality Assurance can provide a sample of an appropriate form to use)

3.3.13.3 Change Evaluation (level 3)

Review this section to ensure it includes:

- The name and organization of the individual(s) who is responsible to evaluate the request for change (In many cases, a change control board is responsible to determine whether a change can be contained within the current project plan)

- Change evaluation criteria such as the nature of the requested change, time estimates to perform, and an impact analysis on the current schedule and plan

3.3.13.4 Change Approval (level 3)

This section defines the procedure for change approval including:

- The name and organization of the individual(s) who is authorized to make decisions as to the disposition of evaluated changes

- The acceptable disposition of the change request; e.g., make the requested change, hold the change for a future release, or reject the change

3.3.13.5 Auditing (level 2)

This section deals with ensuring that the SDM plan is being followed.   Look for evidence demonstrating change against the previously identified baselines is being managed.   Typically, all changes are recorded in the project's change control log.  Other complementary documents such as two-way memos, E-mail notes and messages, and internal forms might also exist.

3.3.13.6 Change Control Log (level 2)

Review the project's change control log to:

- Confirm the change activity is being properly recorded and controlled

- Ensure all changes to the project baseline have been evaluated, approved, and noted

- Ensure the impact of accepted changes has been adequately reflected in the project plan, particularly in revised estimates

3.3.13.7 Re-baseline Requirements (level 2)

Review this section to ensure any changes, additions, or deletions of requirements are properly identified and recorded.  The new baseline consists of the agreed-to set of requirements from the prior phase, plus or minus any requirements from the current phase of development.  The project plan in terms of schedule and budget must reflect the new baseline.

Appendix A

| ###### IPA Report |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name |  |  |  |  |  |  |  |
| Phase |  |  |  |  | Date |  |  |
| Reviewer |  |  |  |  | Phone Number |  |  |
| Number | Issues/Concerns |  |  |  |  |  | Resolved |
| Number | Corrective Action Recommendations |  |  |  |  |  |  |
| Assessment of Risk to Schedule |  |  |  |  |  |  |  |
| Low |  |  | Medium | High |  |  |  |
|  |  |  |  |  | For the next phase |  |  |
|  |  |  |  |  | For the remainder of the project |  |  |

Refresh Schedule

All guidelines and referenced documentation identified in this standard will be subject to review and possible revision annually or upon request by the DPW Information Technology Standards Team.

Guideline Revision Log

| ###### Change Date | ###### Version | ###### Change Description | ###### Author and Organization |
| --- | --- | --- | --- |
| 03/01/1999 | 1.0 | Initial creation | Original SDM team |
| 09/01/2005 | 2.0 | Change to DPW Business and Technical Standards format. Updated the document to align with version 2.0 of the SDM | PMO-DCSS |
| 01/04/2007 | 2.0 | Reviewed content – No change necessary | PMO-DCSS |
| 06/15/2007 | 2.1 | Format Change | PMO-DCSS |
| 02/14/2011 | 2.2 | Removed invalid reference; updated hyperlink | PMO-DEPPM |
| 12/17/2014 | 2.3 | Changed DPW to DHS and other minor changes | PMO-DEPPM |
| 03/29/2016 | 2.3 | Yearly Review and fix links | PMO-DEPPM |