COMMONWEALTH OF PENNSYLVANIA

DEPARTMENT OF HUMAN RESOURCES

INFORMATION TECHNOLOGY GUIDELINE

| Name Of Guideline: | Number: |
| --- | --- |
| Phase Exit Process Guide | GDL-EPPM004 |
| Domain: | Category: |
| Business | Guidelines |
| Date Issued: | Issued By: |
| 03/01/1999 | DHS Bureau of Information Systems |
| Date Revised: |  |
| 03/09/2016 |  |

Table of Contents

Introduction	3

Purpose	3

1.0 Overview	3

Applicability	3

Timing/Frequency	4

Diagram	4

Process Ownership	4

Change Control	4

Relationship to Other System Development Processes	4

Process Measurements	5

2.0 Process	5

Scope	5

Stakeholders	5

Input Providers	6

Input	6

Phase Exit Process Flow	6

Plan Phase Exits	7

Schedule Phase Exit	7

Distribute Materials	7

Receive Positions	7

Prepare Action Plans	8

Conduct Exit Meeting	8

Output	8

Meeting Outcome	9

Management Briefings	9

Responsibility Matrix	10

Appendix A:  Phase Exit Notification Memo	11

Appendix B:  Phase Exit Position Response Form	12

Appendix C:  Phase Exit Distribution List	13

Refresh Schedule	14

Guideline Revision Log	14

Phase Exit Process Guide

Introduction

The Department of Human Services (DHS) Software Development Methodology (SDM) describes the standard system development lifecycle (SDLC) methodology used for systems developed and maintained for DHS.  For better manageability and control, each system development effort is organized into logical, related segments called phases.  Each phase must be officially exited (approved) before the next phase can begin.  The decision points at the end of each phase are called Phase Exits.

Purpose

The purpose of a Phase Exit is to:

- Allow all functional areas involved with the project to review the current project plan.  This includes, at a minimum, a detailed plan for the next phase, and high-level plans for the remainder of the project.

- Provide a forum to raise qualifications (issues and concerns) if issues exist that will impact the project plan.

- Ensure an acceptable action plan exists for all qualifications raised.

- Obtain concurrence on current phase deliverables, and to begin the next phase of development.

1.0 Overview

A Phase Exit is the vehicle for securing the concurrence (i.e., approval) of designated individuals to continue with the project and move forward into the next phase of development or maintenance.  The concurrence is an approval (sign-off) of the deliverables for the current phase of development including the project plan.  It indicates all qualifications (issues and concerns) have been closed or have an acceptable plan for resolution.

Applicability

This process is applicable to all system development and maintenance efforts following the SDM.

Timing/Frequency

A Phase Exit is conducted at the end of each phase of development or maintenance.

Diagram

The following diagram shows the timing of Phase Exits, relative to the SDLC.

###### Phase Exits

| ###### Planning |  |  | ###### Requirements ###### Definition |  |  | ###### General ###### System ###### Design |  |  | ###### Detailed ###### System ###### Design |  |  | ###### Development |  |  | ###### Software ###### Integration ###### & Testing |  |  | ###### Acceptance ###### & ###### Installation |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

###### SDLC

Process Ownership

The responsibilities of the Phase Exit process sponsor include approving the initial process definition document and changes during process improvement.  The responsibilities of the process owner include ensuring the process is working once implemented, and conducting ongoing process improvement.

Change Control

The Phase Exit process is a component of the SDM.  Changes to this process will be instituted using the same change mechanism implemented to process changes to the SDM.  Direct all requests for change to the Program Management Office.

Relationship to Other System Development Processes

The Phase Exit process is a primary component of DHS’s SDLC.  Together with other processes it serves to ensure a consistent and predictable outcome in the resulting software.  The Phase Exit process is complementary to other processes such as In-Phase Assessments and Structured Walkthroughs.

Process Measurements

Process measurements define the measurements to allow for determining the effectiveness of the process at work.  The main process measurement vehicle will be qualifications (issues) raised and closed.  For each phase, the following qualification data will be collected:

- Quantity

- Severity Level

- Low

- Medium

- High

- Qualifications Closed

- Qualifications Remaining Open

2.0 Process

Scope

The Phase Exit process begins with a notification to the extended development team (e.g., project sponsor, user point-of-contact, support areas) a phase exit has been scheduled.  The process ends with the receipt of concurrence from the designated approvers to proceed to the next phase.  Concurrence indicates all known issues have an acceptable plan for resolution.

Stakeholders

The stakeholders of the Phase Exit process are those individuals or organizations using the output of the process.  The primary stakeholders are:

- Division of Application and Development

- Project sponsor

- User point of contact (POC)

- Quality Assurance (QA)

- Information Architecture (IA)

- DHS Security

Input Providers

The following individuals or organizations provide input to the Phase Exit process:

- Project Sponsor

- Project Management Team

- User POC

- QA

- Support areas

Input

The following are the minimum inputs to the Phase Exit process:

- System development lifecycle deliverable(s)

- Initial project plan developed during the planning phase

- Updated project plan revised during all subsequent phases

- Issues to be addressed (generic)

- Qualifications from the approvers

- Issues remaining open from the In-Phase Assessment

Phase Exit Process Flow

The following chart depicts the phase exit process flow:

| ###### Planning Phase |  |
| --- | --- |
| Plan Project’s Phase Exits | Phase Exit Milestones defined in the Project Plan for each SDM phase |
| ###### All Phases |  |
| Schedule Current Exit | Schedule exit for the current phase; notify participants |
| Distribute Current Project Plan | Distribute current project plan and any other items needed to exit phase |
| Receive Positions | Receive positions and qualification (if any) from participants |
| Prepare Action Plans | Present plans for addressing qualifications and secure concurrence |
| Conduct Closure Meeting | Present plans for addressing qualifications and secure concurrence |
| ###### Periodic |  |
| Brief Project Sponsor | Provide a briefing of status, issues, risks, from the QA perspective |

Plan Phase Exits

In the Planning phase, the planned date for exiting each phase of development is identified and documented in the project plan.  It is common practice for the Phase Exit date for the next phase to be more specific and the dates for subsequent phases to be high level milestones.

Schedule Phase Exit

For each phase, as soon as practical, establish the actual Phase Exit date and the exit meeting scheduled.  Two or three weeks prior to the exit meeting, a memo or email is sent to all persons participating in the phase exit to communicate the following information:

- Notify participants a phase exit has been scheduled.  Participants include approvers (e.g., project sponsor), project management team, and individuals with a need to know (e.g., contractor management).

- Request the approvers provide feedback one week before the exit meeting.  This will allow the project manager time to work issues and develop action plans prior to the exit meeting.

- Invite participants to attend the exit meeting.

Templates for the Phase Exit Notification Memo, Phase Exit Response Form, and Phase Exit Distribution List are provided in the Appendices.

Distribute Materials

Distribute the current project plan, and any other material relevant to exiting the phase to the participants along with the memo.  Relevant materials include, for example, known issues, and unplanned deliverables.

The participants should be familiar with planned deliverables (e.g. the Requirements Definition Document (RDD) in the Requirements Definition phase) since it is common practice for them to review drafts as they are developed.  If this is not the case, then planned deliverables also need to be distributed at this time.

The project plan is dynamic and typically undergoing changes up to the last minute, and is distributed (together or under separate cover) at the same time as the phase exit notification memo.

Receive Positions

A position is required from the list of approvers.  This position can be concur, concur with qualifications, or non-concur.  The implication of each is as follows:

- Concur - Proceed with the project according to the current plan.  An example would be where the approver is not aware of any issues for the current phase.

- Concur with qualifications - There are issues or concerns.  The project can proceed according to the current plan if an acceptable action plan is developed for each issue by the phase exit meeting.  An example would be where there is no plan for testing an interface to an existing system being changed.

- Non-concur - There are very significant issues or concerns.  The project should not move to the next phase until issue(s) are resolved.  An example would be where funding for the project has been withdrawn or not appropriated.

All qualifications (issues/concerns) must be communicated to the project manager.  The position response form contains space for this purpose; however other forms of communication may be used.

Responses are not required from individuals in the "Support" or "Information" categories of the distribution list; however, they are encouraged to review the deliverables and provide feedback having an impact on the project plan.

Prepare Action Plans

The project manager must prepare an action plan to address each qualification received.   Sometimes action plans extend beyond the phase exit milestone.  This is acceptable, if it will not negatively impact the current project plan.  These action plans are then presented at the phase exit meeting.

Conduct Exit Meeting

At the exit meeting, the project manager presents positions from the approvers, along with qualifications raised during the phase exit process, and issues remaining open from the In-Phase Assessment (IPA).  Action plans must also be presented for each qualification or issue.  The objective is to demonstrate all issues have been resolved, the current plan is sound, and the project is under control.

The results of the meeting are documented in summary form, and include positions, qualifications, action plans, and follow up activity.

Output

The output produced when the Phase Exit process is executed consists of:

- Positions from the approvers

- Qualifications (if any) from review of the deliverables

- Action plans to resolve all qualifications/issues.

Meeting Outcome

The results of the exit meeting will determine the next step in the development process. The project will proceed in one of the following directions:

- Project proceeds to the next phase according to plan.  There were no qualifications raised.

- Project proceeds to the next phase according to plan.  All qualifications raised had an acceptable action plan.

- Project cannot proceed to the next phase because significant issues were raised that do not have acceptable action plans to resolve; e.g., funding withdrawn.  Schedule a follow-up exit meeting to review action plans and reach concurrence to proceed.

Management Briefings

Periodically, (e.g. quarterly) the project manager or quality assurance analyst will brief the project sponsor regarding the health and well being of the project, from the QA analyst's perspective.  This will minimize the possibility of any surprises later and, if issues exist, they can be addressed timely.  The briefing covers:

- Project status

- Issue(s) (if any)

- Project risk(s)

- Action(s) required to remove issues or mitigate risk

Responsibility Matrix

The following matrix defines the responsibilities for the various organizations involved in the Phase Exit process.

|  | ###### Project Manager | ###### Support Areas | ###### Quality Assurance | ###### Project Sponsor | ###### User | ###### Project Management Team | ###### Process Owner/Team |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Schedule Phase Exit | P |  | R |  |  |  |  |
| Distribute current project plan and other materials | P |  |  |  |  |  |  |
| Review project plan, etc. |  | R | R | R | R | R |  |
| Concur/non-concur |  |  | P | P | P | P |  |
| Prepare action plan | P |  |  |  |  |  |  |
| Conduct exit meetings | P |  | S |  |  |  |  |
| Monitor process effectiveness |  |  | P |  |  | S |  |
| Continuous process improvement | S |  | S |  | S | P |  |

Legend

P=Perform	    R=Review     S=Support

Appendix A:  Phase Exit Notification Memo

###### Phase Exit Notification Memo

Date:

To: Distribution list

From: [project manager]

Subject: [phase name] Phase Exit

The [phase name] Phase Exit for [project name] has been scheduled.  The exit meeting will be held on [date], from [start time] to [end time], at [location including room number].  Positions, qualifications, and action plans will be reviewed at this meeting.

The review material is [attached or has been distributed previously].  A response is required by [date] from those persons designated as approvers on the distribution list.  All others are encouraged to provide feedback and attend the exit meeting.  The approver's response may be a position of concur, concur with qualifications (issues), or non-concur.  A position form is attached for your convenience.  If no response is received, a position of concur will be assumed for the approver.

If you have any questions, please contact me at [area code/phone number or electronic address] or [alternate name, phone number] for assistance.

[sign here if hardcopy]

Project Manager

Attachment

cc: Distribution list (attached)

Project notebook/file

(memo only)

[list individuals as appropriate]

Appendix B:  Phase Exit Position Response Form

| ###### Phase Exit Position Response Form |  |  |  |
| --- | --- | --- | --- |
| Project Name |  |  |  |
| Project Phase |  |  |  |
| Return Form To |  |  |  |
| Return By |  |  |  |
| Return By |  |  |  |
| Position |  |  |  |
|  | Concur |  | Proceed with the project according to plan |
|  | Concur with qualifications |  | Issue(s) exist. The project can proceed according to the current plan if there is an acceptable action plan for each issue by the stage exit meeting. |
|  | Non-concur |  | Significant issue(s) exist. The project should not proceed to the next stage until the issue(s) is/are resolved. |
| Qualifications |  |  |  |
| Approver |  |  |  |
| Signed |  |  |  |
| Date |  |  |  |

Appendix C:  Phase Exit Distribution List

| ###### Phase Exit Distribution List |  |  |
| --- | --- | --- |
| ###### Distribution List |  |  |
| Approval | Roll or Responsibility | Function |
|  |  | Concurs the project is ready to proceed into the next phase, based on completed deliverables for the current phase, a sound revised project plan for the next phase, and no open issues. |
| Support | Roll or Responsibility | Function |
|  |  | Reviews revised project plan for their functional area involvement and services the project is dependent upon. Provides feedback to the project manager. |
| Information | Roll or Responsibility | Function |
|  |  | Provided for information purposes. Feedback is welcome, but not required. |

Refresh Schedule

All guidelines and referenced documentation identified in this standard will be subject to review and possible revision annually or upon request by the DHS Information Technology Standards Team.

Guideline Revision Log

| ###### Change Date | ###### Version | ###### Change Description | ###### Author and Organization |
| --- | --- | --- | --- |
| 03/01/1999 | 1.0 | Initial creation | Original SDM team |
| 09/01/2005 | 2.0 | Change to DPW Business and Technical Standards format. Updated the document to align with version 2.0 of the SDM | PMO-DCSS |
| 01/04/2007 | 2.0 | Reviewed content- No changes | PMO-DCSS |
| 06/15/2007 | 2.1 | Format Change | PMO-DCSS |
| 02/15/2011 | 2.2 | Reviewed Content – No changes | PMO-DCSS |
| 12/16/2014 | 2.3 | Change DPW to DHS and other minor corrections | BIS-DEPPM |
| 03/09/2016 | 2.3 | Annual Review | BIS-DEPPM |

In the Planning Phase, the distribution list must include all support areas.  In subsequent phases, only the support areas involved.