## Slide 1: DHS Bureau of Hearings and Appeals (BHA) Hearings and Appeals Tracking System (HATS) Decommissioned: July 2007
Lessons Learned Storyboard Presentation
Notes: <number>

## Slide 2
Review Period Overview
Milestones/Deliverables
Activities
What Worked
Improvements
Future Activities
Summary
AGENDA
Notes: <number>

## Slide 3: Review Period Overview
<number>
Purpose:
  To create and implement a cost-effective solution for tracking hearings and appeals cases, using a customized Commercial-Off-The-Shelf (COTS) software product.
Objectives:
  The objective of the HATS project was to implement a case tracking solution that would eliminate duplicative data entry into multiple systems, and to replace outdated and unsupported existing applications solutions (Access and MAPPER).
  The review period covers the project from inception in early 2000 through decommissioning in mid-2007.
  All phases of the project from Strategy to Close-out are covered in this review.
Notes: <number>

## Slide 4: Milestones
<number>
Strategy and Initiation Phase Conducted: 2000 – 2002
Planning Phase Conducted: 2003 – 2004
Vendor contract initiated: 03/2004
JAD Sessions: 10/2004, with Development throughout 2005
UAT: 2006
Pilot: May 2007
Viability Study: June 2007
Recommendation to Decommission: September 2007

## Slide 5: Deliverables
<number>
No formal deliverables were identified in the Lessons Learned Process, but it was established that the project was fixed-price, deliverables-based.
The test product was provided to BIS in December of 2005. Various subsequent versions were also provided during UAT in 2006.
Project documentation was maintained by individual project team members.

## Slide 6: Activities/Work Processes
<number>
Governance Structure:
  A Primary Project Team was assembled with participants from BHA, BIS-DEA, and the vendor.
Meetings:
  Project team meetings were conducted, but not on a regular or frequent basis.
Vendor Liaison:
  A program office and BIS representative served as the primary contacts for vendor management and interaction.
UAT:
  Organized and documented.

## Slide 7: Roadblocks/Delays
<number>
People:
  Significant vendor staff turnover.
  No ONE person managing the project.
  Lacking cross-program participation/management. Missing key areas.
  Lack of executive sponsorship.
  Staff morale issues.
Communications:
  Time lapse caused the team to lose sight of their goals.
  Physical locations of team members, vendor, and other key stakeholders.
  Steering committee out of the loop in key decisions.

## Slide 8: Roadblocks/Delays
<number>
Requirements:
  Conflicts between JAD and Requirements.
  Evolution of requirements, scope change.
  COTS product modified approximately 40%
Project Management:
  Project Management Lifecycle not followed (EPMM)
  Risks not identified early on
  Version control issues with code and database
  Staff training conducted four times, BEFORE code was fully developed
  Vendor management issues

## Slide 9: What Worked
<number>
A modified Governance structure was established early in the process.
Project team was committed to the project.
BIS business knowledge, vendor coordination, and translation of technical jargon.
Active cooperation between OIG & OIM
These successes will be repeated through organizational commitment, planning, and effective communications.

## Slide 10: Improvements
<number>
Secure sponsorship at the Executive level to ensure visibility, project commitment, and funding.
Utilize BIS support for vendor selection process using defined criteria and a proven procurement process.
Identify and include ALL stakeholders in advance and include them in all phases of the project from inception to implementation (comprehensive Project Governance).
Follow the formal Enterprise Project Management Methodology (EPMM), with a dedicated Project Manager.
Create and follow a proven Change Management and Risk Management Plan.
Use technology to improve coordination and limit travel requirements (e.g. Live Meeting, Webinar, shared document repository).

## Slide 11: Future Activities
<number>
The documents associated with the Lessons Learned session have been distributed to the Project Team, BIS Management, and BHA Management.
These documents will also be stored within BIS’ SharePoint site for use on future BHA initiatives.
Operational issues outside of the scope of this session were addressed at the meeting. These issues are primarily related to desktop and phone support issues. This information has been escalated within BIS and will be addressed accordingly.
An internal feasibility study will be conducted to determine how best to proceed with identifying a solution that will meet the business needs.

## Slide 12: Summary
<number>
The Hearings and Appeals Tracking System project was established to provide a cost-effective solution for case tracking that would eliminate duplicative data entry and replace out-dated technologies.
Due to a myriad of problems that occurred over the lengthy duration of this project, it was determined that the final solution did not meet the needs of the organization. As a result, the solution was abandoned.
During the time that the project was in the Execution Phase, many process and organizational advancements have been made in the areas of IT procurement, product selection, and project and program management. These processes will significantly aid BHA and BIS on future technology initiatives.

## Slide 13: Questions & Answers
<number>