## Slide 1
Traffic control-stage 1B&1C
22
Work Zone
Completed Construction
West Central Ave.
East Central Ave.
Lancaster Ave.
North Valley Rd.
Train Station
Half width construction with one lane open to homes at all times.
Revised 2-12-24

## Slide 2
Traffic control-stage 1D
24
Work Zone
Completed Construction
- Temporary traffic signal installed at Central Ave/North Valley Rd.
West Central
Ave.
East Central Ave.
Lancaster Ave.
North Valley Rd.
Train Station
- Half width construction with one lane open through to Knob Hill Lane for large trucks & EMS at all times.
Revised 2-12-24

## Slide 3
Traffic control-Detour
25
NB Detour (3 miles)
SB Detour (3 miles)
Road Closure Area
(road open for large trucks and EMS)
North Valley Road Detour

## Slide 4
Traffic control-stage 1E&1F
26
Work Zone
Completed Construction
- Temporary traffic signal installed at Central Ave/North Valley Rd.
West Central Ave.
East Central Ave.
Lancaster Ave.
North Valley Rd.
Train Station
- Half width construction with one lane open to homes at all times.

## Slide 5
Traffic control-stage 2A&2B
28
Work Zone
Completed Construction
- Temporary traffic signal installed at Central Ave/North Valley Rd.
Traffic switched to new bridge and roadway
Existing Bridge removed
Train station and parking remains open.
West Central Ave.
East Central Ave.
Lancaster Ave.
North Valley Rd.
Train Station
- Access to business and residential driveways to be maintained during construction.
Revised 2-12-24

## Slide 6
Traffic control-stage 3&4
29
Stage 3 – Install islands at roundabout
Stage 4 – Final paving of all project areas
Work Zone
Completed Construction
West Central Ave.
East Central Ave.
Lancaster Ave.
North Valley Rd.
Train Station
- Access through to Knob Hill Lane for large trucks & EMS at all times.
Revised 2-12-24

## Slide 7
detour
30
EB Detour (4.1 miles)
WB Detour (4.1 miles)
Road Closure Area
(road open for large trucks and EMS)
North Valley Rd./Central Ave Int. Detour
Revised
2-12-24